## Changelog
SteelBuild Pro Action Plan — Changelog
As of | 2026-07-25
Source | Updated from docs/action-plan/TASK_LEDGER.md + WORK_NEXT_SLICE.md (withProjectId) + merges #114–#121
Key completions since 2026-07-23 workbook
PR #114–#117: Piece Register restore, PMA removal, drawing/fab, piece-control, launch-readiness — on main + prod
PR #119: Action-plan hygiene, LS-auth removal, mutation helpers, ResourceScheduling helpers, Sentry fixes — merged + prod deploy
PR #120: TypeScript standard + priority business-rule TS conversions + check:no-new-js — merged + prod
Hosted migrations applied including 20260724120000/130000/140000/150000
Production: https://www.steelbuild-pro.com (deploy after #119)
Remaining blockers: staging UAT credentials, GitHub Actions billing limit, large-page thinning, universal mutation adoption (ID 50)
Status counts (Tracker)
Done | 79
In Progress | 25
Blocked | 1
Total tasks | 105
2026-07-25 next-slice: withProjectId write shaping on high-traffic creates; Done IDs 19/43/64/68/70/84/89/92/94/95/97/99/103-105
2026-07-26 | cursor/action-plan-next-slice-d3a1 | Adoption continuation: Submittals mutation helpers; withProjectId on CO/SOV/Procurement/Documents/Submittals; toUserErrorMessage on field/commercial toasts. IDs 21/48/50/52 remain Partial.
2026-07-26 | cursor/action-plan-next-slice-d3a1 | RFI mutation helpers (ID 23); withProjectId on ActionItems/DailyLogs/Constraints/LookAhead/WPs/FieldToday photos/EscalateModal/emailInbox.
2026-07-26 | cursor/action-plan-next-slice-d3a1 | Drawings mutation helpers (ID 27); withProjectId on FabRelease/ContractManagement/Schedule MPP import/comment dispositions/Deliveries alerts.
2026-07-26 | PR #123 merged + prod deploy | withProjectId + mutation helpers (Submittals/RFIs/Drawings) + tracker Done 78 / IP 26 / Blocked 1. Local gates green; GH Actions billing still blocked.
2026-07-26 | cursor/action-plan-photos-safety-loading-d3a1 | ID 18: Photos + Safety INLINE LoadingSkeleton + error/empty gates (no RegisterFetchBody dep; complements PR #133).
2026-07-26 | field-loading | Inspections INLINE gates + ProductionNote withProjectId; Done 79 / IP 25 / Blocked 1

## Tracker
ID | Workstream | Task | Owner | Priority | Status | Due Week | Target Date | Week Start | Notes
1 | Immediate Stabilization | Identify every duplicated module under src/<module> and src/components/<module> | Engineering | Critical | Done | Week 1 | 2026-07-25 | 2026-07-25 | Completed 2026-07-24. Duplicate inventory in docs/action-plan/DUPLICATE_INVENTORY.md (PR #119).
2 | Immediate Stabilization | Choose one canonical location for each duplicated file | Engineering | Critical | Done | Week 1 | 2026-07-26 | 2026-07-26 | Completed 2026-07-24. Canonical ownership chosen; see DUPLICATE_INVENTORY.md + folder-ownership.md.
3 | Immediate Stabilization | Replace duplicate copies with imports/re-exports temporarily | Engineering | Critical | Done | Week 1 | 2026-07-27 | 2026-07-27 | Completed 2026-07-24. Risky duplicates replaced with re-exports (e.g. ImpactBoard → Panel).
4 | Immediate Stabilization | Delete stale duplicate implementations after verification | Engineering | High | Done | Week 2 | 2026-07-28 | 2026-07-28 | Completed 2026-07-24. Deleted dead viewer/**, WeeklySummary orphans, app-params.js, AuthCallbackError, BulkActionBar.
5 | Immediate Stabilization | Document final folder ownership rules | Engineering | High | Done | Week 2 | 2026-07-29 | 2026-07-29 | Completed 2026-07-24. docs/architecture/folder-ownership.md published.
6 | Broken Workflow Fixes | Confirm task creation no longer causes disappearing records | Engineering / QA | Critical | Done | Week 1 | 2026-07-30 | 2026-07-30 | Completed 2026-07-24. Task persistence sanitize + taskPersistence.test.ts (PR #119).
7 | Broken Workflow Fixes | Fix cost codes save behavior | Engineering | Critical | Done | Week 1 | 2026-07-23 | 2026-07-31 | Completed earlier + re-verified. costCodeSave + soft-delete + unique index migration 20260724140000.
8 | Broken Workflow Fixes | Fix contracts save behavior | Engineering | Critical | Done | Week 1 | 2026-07-23 | 2026-08-01 | Completed earlier + re-verified. ContractManagement + projectUpdateEvents.
9 | Broken Workflow Fixes | Fix change order edit behavior | Engineering | Critical | Done | Week 1 | 2026-07-23 | 2026-08-02 | Completed earlier + re-verified. changeOrderPayload whitelist + tests.
10 | Broken Workflow Fixes | Fix change order delete behavior | Engineering | Critical | Done | Week 1 | 2026-07-23 | 2026-08-03 | Completed earlier + re-verified. CO archive/soft-delete in CoControlCenter.
11 | Broken Workflow Fixes | Fix checklist item behavior | Engineering | Critical | Done | Week 1 | 2026-07-23 | 2026-08-04 | Completed earlier + re-verified. closeoutPayload mapping + tests.
12 | Broken Workflow Fixes | Fix PMA nonfunctional paths | Engineering | Critical | Done | Week 1 | 2026-07-23 | 2026-08-05 | Completed 2026-07-24. PMA removed from runtime (UI/routes/clients/tests); pmaRemoval.test.ts. Deployed to prod.
13 | Broken Workflow Fixes | Audit drawing workflow pain points and list exact failures | Engineering / PM | High | Done | Week 1 | 2026-07-23 | 2026-08-06 | Completed 7/21/2026. Drawing workflow failures were isolated and documented; PDF render race corrected in PR #96 with viewer regression tests.
14 | Broken Workflow Fixes | Verify SteelBuild-Pro sync reliability | Engineering | Critical | Done | Week 1 | 2026-08-07 | 2026-08-07 | Completed 2026-07-24 (hardened). SharePoint Sync Now honesty (no last_sync_at bump, sync_enabled=false); shipping-list piece-sync warnings; shipping-ticket deliveries-only copy; Data Exchange skipped-create reporting. See WORK_14_17.md.
15 | Broken Workflow Fixes | Retest all corrected flows end to end | QA | Critical | Done | Week 1 | 2026-08-08 | 2026-08-08 | Completed 2026-07-24 for automated retest. npm run test:corrected-flows — 18 files / 155 tests PASS. Report: RETEST_CORRECTED_FLOWS.md. Interactive staging UAT still ID 102.
16 | Runtime Stability | Find and fix remaining React hook-order violations | Engineering | Critical | Done | Week 1 | 2026-08-09 | 2026-08-09 | Completed 2026-07-24. ESLint react-hooks/rules-of-hooks clean across src/; npm run check:hooks. AST scan of large pages found 0 early-return-before-hooks.
17 | Runtime Stability | Review console errors and warnings across major pages | Engineering / QA | High | Done | Week 1 | 2026-08-10 | 2026-08-10 | Completed 2026-07-24. Reviewed unresolved Sentry (javascript-react). Residual: CSP-RO vercel.live/inline noise, staging EnvValidation (ops), pre-deploy model-elements timeouts (monitor post-#119). See WORK_14_17.md.
18 | Runtime Stability | Add loading, empty, and error states to critical modules | Engineering | High | Done | Week 2 | 2026-08-11 | 2026-08-11 | Done 2026-07-26. Photos/Safety INLINE + thin CRUD RegisterFetchBody (#133/#137); Inspections INLINE + ProductionNotes skeleton. Not universal.
19 | Runtime Stability | Add fallback handling for null project / null entity states | Engineering | High | Done | Week 2 | 2026-08-12 | 2026-08-12 | Completed 2026-07-25. Null-project guards + withProjectId/assertProjectId on high-traffic creates (field/QC/schedule/drawings/expenses/budget/resources/transmittals).
20 | Runtime Stability | Verify modals and drawers do not break on missing data | QA | High | In Progress | Week 2 | 2026-08-13 | 2026-08-13 | Modal/drawer project-switch safety varies by module; needs interactive UAT.
21 | Codebase Cleanup | Refactor src/pages/Submittals.jsx | Engineering | Critical | In Progress | Week 2 | 2026-08-14 | 2026-08-14 | Partial 2026-07-26. submittalMutationHelpers extracted + tested; withProjectId on create/round/sheet/bulk. Shell still ~1k LOC.
22 | Codebase Cleanup | Refactor src/pages/Constraints.jsx | Engineering | High | In Progress | Week 3 | 2026-08-15 | 2026-08-15 | Constraints already split under pages/constraints/; shell ~403 LOC.
23 | Codebase Cleanup | Refactor src/pages/RFIs.jsx | Engineering | Critical | In Progress | Week 2 | 2026-08-16 | 2026-08-16 | Partial 2026-07-26. rfiMutationHelpers extracted + tested; create/alert/doc attach use withProjectId. Shell still ~600 LOC.
24 | Codebase Cleanup | Refactor src/pages/ResourceScheduling.jsx | Engineering | High | Done | Week 3 | 2026-08-17 | 2026-08-17 | Completed 2026-07-24. Pure helpers extracted to pages/resourceScheduling/resourceSchedulingHelpers.ts (+27 tests); page is orchestrator (PR #119).
25 | Codebase Cleanup | Refactor src/Layout.jsx | Engineering | High | In Progress | Week 3 | 2026-08-18 | 2026-08-18 | Layout reduced to shell (~429 LOC); further thinning optional.
26 | Codebase Cleanup | Refactor src/pages/Deliveries.jsx | Engineering | High | In Progress | Week 3 | 2026-08-19 | 2026-08-19 | Deliveries already split under pages/deliveries/; further extraction optional.
27 | Codebase Cleanup | Refactor src/pages/Drawings.jsx | Engineering | Critical | In Progress | Week 2 | 2026-08-20 | 2026-08-20 | Partial 2026-07-26. drawingMutationHelpers extracted + tested; create/delete-set toast helpers. Shell still ~1k LOC; hub remains canonical.
28 | Repo Hygiene | Remove stale root-level duplicate folders | Engineering | High | Done | Week 2 | 2026-08-21 | 2026-08-21 | Completed 2026-07-24. No stale root duplicate folders found.
29 | Repo Hygiene | Remove old zip/tgz artifacts from repo workflow | Engineering | Medium | Done | Week 2 | 2026-08-22 | 2026-08-22 | Completed 2026-07-24. No tracked zip/tgz; .gitignore blocks archives.
30 | Repo Hygiene | Remove logs from tracked workspace | Engineering | Medium | Done | Week 2 | 2026-08-23 | 2026-08-23 | Completed 2026-07-24. Logs ignored; none tracked.
31 | Repo Hygiene | Remove or isolate dist from source repo workflow | Engineering | Medium | Done | Week 2 | 2026-08-24 | 2026-08-24 | Completed earlier. dist/ untracked via .gitignore.
32 | Repo Hygiene | Confirm .env.local is not exposed improperly | Engineering | Critical | Done | Week 2 | 2026-08-25 | 2026-08-25 | Completed earlier. Only .env.example tracked; secrets not in git.
33 | Repo Hygiene | Update .gitignore if needed | Engineering | Medium | Done | Week 2 | 2026-08-26 | 2026-08-26 | Completed 2026-07-24. .gitignore extended (coverage, archives, playwright, /exports/ anchor).
34 | Repo Hygiene | Clean repo for multi-developer work | Engineering | High | Done | Week 2 | 2026-08-27 | 2026-08-27 | Completed 2026-07-24. Single package-lock.json; contributor docs cleaned.
35 | Structure Standardization | Define folder rules for pages/components/hooks/services/utils/entities | Engineering Lead | High | Done | Week 2 | 2026-08-28 | 2026-08-28 | Completed 2026-07-24. Folder rules in docs/architecture/folder-ownership.md.
36 | Structure Standardization | Move shared UI to one shared location | Engineering | High | In Progress | Week 3 | 2026-08-29 | 2026-08-29 | Shared UI in design-system/ + components/ui; some page-local FilterBar/EmptyState retained intentionally.
37 | Structure Standardization | Move workflow logic out of generic UI folders | Engineering | High | In Progress | Week 3 | 2026-08-30 | 2026-08-30 | Business logic extraction ongoing; mutation helpers + ResourceScheduling helpers landed.
38 | Structure Standardization | Publish short architecture note for future edits | Engineering Lead | Medium | Done | Week 3 | 2026-08-31 | 2026-08-31 | Completed 2026-07-24. Architecture notes: folder-ownership.md + typescript-standard.md (PR #120).
39 | Engineering Discipline | Confirm local lint script works consistently | Engineering | Critical | Done | Week 1 | 2026-09-01 | 2026-09-01 | Completed 7/21/2026. Local lint repeatedly passed across PRs #92-#108 and is enforced in CI.
40 | Engineering Discipline | Confirm local typecheck script works consistently | Engineering | Critical | Done | Week 1 | 2026-09-02 | 2026-09-02 | Completed 7/21/2026. Local typecheck and expanded type gates repeatedly passed across PRs #92-#108.
41 | Engineering Discipline | Fix highest-risk lint errors first | Engineering | High | Done | Week 2 | 2026-09-03 | 2026-09-03 | Completed 7/21/2026. Highest-risk lint/CI issues were corrected; production CI passed on Node 24 in PR #93.
42 | Engineering Discipline | Fix unused imports and dead code | Engineering | Medium | Done | Week 3 | 2026-09-04 | 2026-09-04 | Completed 2026-07-24. Dead imports/modules removed (viewer orphans, app-params, AuthCallbackError, WeeklySummary).
43 | Engineering Discipline | Fix prop/type/state issues in critical workflows first | Engineering | Critical | Done | Week 2 | 2026-09-05 | 2026-09-05 | Completed 2026-07-25. Critical workflow typing gated in CI (strict + noImplicitAny); priority business-rule modules converted (PR #120). Remaining JS converts when repaired.
44 | Engineering Discipline | Expand type coverage to src/lib, src/api, and src/components/ui | Engineering | High | Done | Week 3 | 2026-09-06 | 2026-09-06 | Completed 7/21/2026. Type validation expanded through JS, strict, and noImplicitAny gates; new findings are enforced while legacy debt remains tracked.
45 | Engineering Discipline | Stop excluding important folders from type validation | Engineering | High | Done | Week 3 | 2026-09-07 | 2026-09-07 | Completed 7/21/2026. Important source and backend areas are included in the expanded validation gates.
46 | Engineering Discipline | Add lint/typecheck to PR workflow or CI | Engineering | High | Done | Week 4 | 2026-09-08 | 2026-09-08 | Completed 7/21/2026. Lint and typecheck gates are active in GitHub CI; PR #93 modernized the workflow to Node 24.
47 | State & Mutations | Create one standard pattern for fetch + transform + save | Engineering | High | Done | Week 3 | 2026-09-09 | 2026-09-09 | Completed 2026-07-24. src/lib/mutations/standardMutation.ts introduced.
48 | State & Mutations | Create one standard pattern for mutation success/error toasts | Engineering | Medium | In Progress | Week 3 | 2026-09-10 | 2026-09-10 | Partial 2026-07-26. toUserErrorMessage across field/commercial/RFIs/ops/email escalate — not universal yet.
49 | State & Mutations | Create one standard pattern for reload/refetch after save | Engineering | High | Done | Week 3 | 2026-09-11 | 2026-09-11 | Completed 2026-07-24. invalidateAfterMutation helper + cacheRegistry.
50 | State & Mutations | Eliminate page-local ad hoc mutation logic | Engineering | High | In Progress | Week 4 | 2026-09-12 | 2026-09-12 | Partial 2026-07-26. ProductionNote.create via withProjectId(row project_id); prior field/commercial/import wiring; #139–#141 open.
51 | State & Mutations | Review optimistic update behavior for reliability | Engineering | High | In Progress | Week 4 | 2026-09-13 | 2026-09-13 | Critical optimistic paths reviewed in prior PRs; not universal.
52 | State & Mutations | Ensure state cannot silently drift from backend truth | Engineering | Critical | In Progress | Week 4 | 2026-09-14 | 2026-09-14 | Partial 2026-07-26. Write shaping advanced across flagship + ops pages; concurrent-edit E2E still open.
53 | Logic Extraction | Extract KPI calculations into utilities/services | Engineering | High | In Progress | Week 3 | 2026-09-15 | 2026-09-15 | Many KPI derives extracted (portfolio/financial/etc.); continue as pages are refactored.
54 | Logic Extraction | Extract entity transformation logic into shared helpers | Engineering | High | In Progress | Week 3 | 2026-09-16 | 2026-09-16 | Payload helpers for CO/cost/closeout/schedule exist; broaden coverage.
55 | Logic Extraction | Extract project-context gating into reusable guards | Engineering | High | Done | Week 3 | 2026-09-17 | 2026-09-17 | Completed 2026-07-24. assertProjectId shared via useAppSecurity.ts + standardMutation (PR #119/#120).
56 | Logic Extraction | Extract repeated badge/status formatting logic | Engineering | Medium | In Progress | Week 4 | 2026-09-18 | 2026-09-18 | Status enums in domain libs; some duplicate pills remain.
57 | Logic Extraction | Reduce major pages to layout + composition | Engineering | High | In Progress | Week 4 | 2026-09-19 | 2026-09-19 | Control-center composition pattern widely used; major pages still thinning.
58 | Security & Config | Review src/api/base44Client.js | Engineering | Critical | Done | Week 2 | 2026-09-20 | 2026-09-20 | Completed 2026-07-24. base44Client gone; AuthCallbackError deleted; leftovers are comments/docs only.
59 | Security & Config | Review src/lib/app-params.js | Engineering | Critical | Done | Week 2 | 2026-09-21 | 2026-09-21 | Completed 2026-07-24. app-params.js deleted; validated env.ts is source of truth.
60 | Security & Config | Eliminate unsafe token sourcing from URL where possible | Engineering | Critical | Done | Week 2 | 2026-09-22 | 2026-09-22 | Completed earlier. No manual URL token parsers; supabase detectSessionInUrl.
61 | Security & Config | Reduce reliance on localStorage for sensitive auth flows | Engineering | High | Done | Week 3 | 2026-09-23 | 2026-09-23 | Completed 2026-07-24. Removed localStorage identity auth fallbacks (useAppSecurity, SystemTab, SecureDeleteDialog).
62 | Security & Config | Replace loose requiresAuth: false patterns where inappropriate | Engineering | Critical | Done | Week 2 | 2026-09-24 | 2026-09-24 | Completed earlier. No requiresAuth: false patterns found.
63 | Security & Config | Ensure business-critical paths require authenticated context | Engineering | Critical | Done | Week 2 | 2026-09-25 | 2026-09-25 | Completed earlier. AuthenticatedApp gates app; PUBLIC_PAGES explicit.
64 | Security & Config | Verify project-level access boundaries are enforced | Engineering / QA | Critical | Done | Week 3 | 2026-09-26 | 2026-09-26 | Completed 2026-07-25. RLS + PROJECT_SCOPED_TABLES + withProjectId write shaping on critical creates. Org model still TECH_DEBT but project boundary enforced.
65 | Security & Config | Document approved auth/config pattern | Engineering Lead | Medium | Done | Week 3 | 2026-09-27 | 2026-09-27 | Completed 7/21/2026. Approved authentication, staging, project visibility, storage, and recovery patterns are documented in repository runbooks.
66 | Backend Hardening | Review backend functions for auth consistency | Engineering | Critical | Done | Week 3 | 2026-09-28 | 2026-09-28 | Completed earlier. stripe/email/llm JWT gates on edge functions.
67 | Backend Hardening | Review unsafe service-role usage | Engineering | Critical | Done | Week 3 | 2026-09-29 | 2026-09-29 | Completed earlier. service_role server-only in edge functions.
68 | Backend Hardening | Confirm project-level checks for sensitive operations | Engineering | Critical | Done | Week 3 | 2026-09-30 | 2026-09-30 | Completed 2026-07-25. Project checks on sensitive creates via withProjectId (forces active project_id). Continues with universal mutation adoption (ID 50).
69 | Backend Hardening | Validate webhook signature checks where applicable | Engineering | High | Done | Week 4 | 2026-10-01 | 2026-10-01 | Completed earlier. Stripe webhook signature + idempotency.
70 | Backend Hardening | Confirm environment variable names and usage are correct | Engineering | High | Done | Week 3 | 2026-10-02 | 2026-10-02 | Completed 2026-07-25. Env names validated via src/lib/env.ts + .env.example. Staging Vercel mis-set (if still present) is an ops fix, not a code naming issue.
71 | UX Trust | Find all 'coming soon' or placeholder operational screens | PM / QA | High | Done | Week 2 | 2026-10-03 | 2026-10-03 | Completed 2026-07-24. Coming-soon inventory documented (COMING_SOON_INVENTORY.md + integrationCatalog).
72 | UX Trust | Hide incomplete features from production users | Engineering | High | Done | Week 2 | 2026-10-04 | 2026-10-04 | Completed earlier. Coming-soon gated in Integrations UI.
73 | UX Trust | Replace placeholders with clear 'not enabled' messaging | Engineering | Medium | Done | Week 2 | 2026-10-05 | 2026-10-05 | Completed earlier. Honest messaging for incomplete connectors.
74 | UX Trust | Remove fake buttons or dead controls | Engineering | High | Done | Week 2 | 2026-10-06 | 2026-10-06 | Completed 2026-07-24. SharePoint Sync Now labeled unavailable (muted) in DocumentStorageSettings.
75 | UX Trust | Ensure every visible feature does something trustworthy | QA | Critical | In Progress | Week 3 | 2026-10-07 | 2026-10-07 | Flagship paths honest; catalog still lists future items intentionally.
76 | Workflow Continuity | Audit drawings workflow end to end | PM / QA / Engineering | Critical | Done | Week 2 | 2026-10-08 | 2026-10-08 | Completed earlier (PR #115). Drawing/submittal/fab controls hardened + tests + migrations; on prod.
77 | Workflow Continuity | Audit RFI workflow end to end | PM / QA / Engineering | Critical | In Progress | Week 2 | 2026-10-09 | 2026-10-09 | RFI path hardened; full field UAT still open.
78 | Workflow Continuity | Audit work package workflow end to end | PM / QA / Engineering | High | Done | Week 3 | 2026-10-10 | 2026-10-10 | Completed earlier (PR #116). Piece/production hardening on prod.
79 | Workflow Continuity | Audit deliveries workflow end to end | PM / QA / Engineering | High | Done | Week 3 | 2026-10-11 | 2026-10-11 | Completed earlier (PR #116). Shipping bridge + quantity rules on prod.
80 | Workflow Continuity | Audit schedule workflow and look-ahead planning | PM / QA / Engineering | High | In Progress | Week 3 | 2026-10-12 | 2026-10-12 | Schedule/look-ahead present; field-verify UAT open.
81 | Workflow Continuity | Audit cost / SOV / budget control workflow | PM / QA / Engineering | Critical | In Progress | Week 3 | 2026-10-13 | 2026-10-13 | Cost/SOV/budget paths exist; KPI reconciliation tests partial.
82 | Workflow Continuity | Audit PMA usefulness inside real PM workflow | PM / QA / Engineering | Critical | Done | Week 3 | 2026-10-14 | 2026-10-14 | Completed 2026-07-24. PMA removal complete at runtime; audit usefulness = N/A (feature retired).
83 | Workflow Continuity | Fix handoff gaps between office, shop, and field surfaces | Engineering | High | In Progress | Week 4 | 2026-10-15 | 2026-10-15 | Nav dead-ends fixed in #117; more office/shop/field handoffs remain.
84 | Project Boundaries | Verify every operational module respects project context | Engineering / QA | Critical | Done | Week 3 | 2026-10-16 | 2026-10-16 | Completed 2026-07-25. PROJECT_SCOPED_PAGES + RLS + withProjectId on operational creates (schedule/drawings/field/cost/resources/transmittals). Interactive project-switch UAT remains ID 88/102.
85 | Project Boundaries | Remove silent cross-project blending in working modules | Engineering | High | Done | Week 3 | 2026-10-17 | 2026-10-17 | Completed 2026-07-24. Explicit named FK project scope (contacts/projects Sentry fix) + softDelete scoping.
86 | Project Boundaries | Separate executive roll-up views from project execution views | Engineering | High | Done | Week 4 | 2026-10-18 | 2026-10-18 | Completed earlier. Portfolio vs project modes on Dashboard.
87 | Project Boundaries | Confirm filters, summaries, and KPIs are scoped correctly | QA | High | In Progress | Week 4 | 2026-10-19 | 2026-10-19 | ListTruncationNotice on some registers; confirm all KPIs scoped.
88 | Project Boundaries | Retest project switching across major pages | QA | Critical | In Progress | Week 4 | 2026-10-20 | 2026-10-20 | Needs interactive project-switch UAT across major pages.
89 | Testing | Create tests for create/edit/delete on core records | QA / Engineering | Critical | Done | Week 4 | 2026-10-21 | 2026-10-21 | Completed 2026-07-25. Core create/edit/delete tests exist for CO/cost/closeout/piece + mutation helpers; expand remaining forms under ID 50/97 as pages adopt standardMutation.
90 | Testing | Add tests for task persistence | QA / Engineering | Critical | Done | Week 4 | 2026-10-22 | 2026-10-22 | Completed 2026-07-24. taskPersistence.test.ts regression coverage.
91 | Testing | Add tests for project context switching | QA / Engineering | High | Done | Week 4 | 2026-10-23 | 2026-10-23 | Completed 7/23/2026. Project-context and cross-project deep-link regression tests added; PR #107 verifies activation before scoped record rendering.
92 | Testing | Add tests for stage advancement | QA / Engineering | High | Done | Week 4 | 2026-10-24 | 2026-10-24 | Completed 2026-07-25. Stage/transition tests for submittal/drawing + fab-release gate present; broaden as stage graphs change.
93 | Testing | Add tests for assignment flows | QA / Engineering | Medium | In Progress | Week 4 | 2026-10-25 | 2026-10-25 | Assignment-flow coverage uneven across modules.
94 | Testing | Add tests for cost calculations and KPIs | QA / Engineering | Critical | Done | Week 4 | 2026-10-26 | 2026-10-26 | Completed 2026-07-25. Cost/KPI calc tests exist (margin, portfolio, cost rollup, etc.).
95 | Testing | Add tests for sync-sensitive workflows | QA / Engineering | Critical | Done | Week 4 | 2026-10-27 | 2026-10-27 | Completed 2026-07-25. Sync-sensitive tests present (production hardening / piece sync). SharePoint connector remains unavailable (honest UI).
96 | Testing | Add tests for drawing revision logic | QA / Engineering | Critical | Done | Week 4 | 2026-10-28 | 2026-10-28 | Completed 7/22/2026. Drawing revision and exact-record link behavior received focused tests in PR #101; viewer render lifecycle tests added in PR #96.
97 | Testing | Add tests for major save forms | QA / Engineering | High | Done | Week 4 | 2026-10-29 | 2026-10-29 | Completed 2026-07-25. Major save-form tests for key domains (cost codes, CO payload, closeout, schedule persistence).
98 | Testing | Add tests for permission-sensitive operations | QA / Engineering | High | Done | Week 4 | 2026-10-30 | 2026-10-30 | Completed 7/23/2026. Permission-sensitive operations have regression coverage for storage, transmittals, piece archival, desktop reads, and service-only handoffs.
99 | Production Readiness | Re-audit all critical modules after refactors | QA / PM | High | Done | Week 5 | 2026-10-31 | 2026-10-31 | Completed 2026-07-25 checkpoint. Re-audit via TASK_LEDGER + Sentry triage + IDs 14–17. Re-open after large page refactors.
100 | Production Readiness | Re-run lint with zero critical issues | Engineering | High | Done | Week 5 | 2026-11-01 | 2026-11-01 | Completed 7/21/2026. Lint rerun successfully with no blocking/critical lint failures in production CI.
101 | Production Readiness | Re-run typecheck with expanded coverage | Engineering | High | Done | Week 5 | 2026-11-02 | 2026-11-02 | Completed 7/23/2026. Expanded TypeScript/JavaScript/strict/noImplicitAny checks pass; legacy findings remain grandfathered and visible.
102 | Production Readiness | Re-test all core workflows | QA | Critical | Blocked | Week 5 | 2026-11-03 | 2026-11-03 | Full core-workflow UAT blocked without authenticated staging session + GitHub Actions billing/spending limit.
103 | Production Readiness | Re-check permissions and auth | QA / Engineering | Critical | Done | Week 5 | 2026-11-04 | 2026-11-04 | Completed 2026-07-25 checkpoint. Auth/permissions re-check (LS identity auth removal, JWT gates, RLS). Continuous verification continues operationally.
104 | Production Readiness | Re-check project boundary enforcement | QA | High | Done | Week 5 | 2026-11-05 | 2026-11-05 | Completed 2026-07-25 checkpoint. Project boundary re-check in code (FK embeds, scoped selects, withProjectId). Interactive retest = ID 102.
105 | Production Readiness | Re-check UI trust and silent failure risk | QA / PM | High | Done | Week 5 | 2026-11-06 | 2026-11-06 | Completed 2026-07-25 checkpoint. UX trust re-check (honest Sync Now, coming-soon inventory, sync honesty ID 14). Catalog future items intentional.
Note on A1: Action-plan tracker generated from the audit/action-plan content in this conversation.

## Summary
SteelBuild Pro Action Plan Dashboard
Plan start | 2026-03-30 12:00 | As of | 2026-07-26 | Completion |  | Open critical
Total Tasks |  | Completed |  | In Progress |  | Blocked
Not Started |  | Ready for QA |  | QA Complete |  | Overdue Open
Workstream | Task Count | Critical | High | Medium | Completed | Open
Backend Hardening
Broken Workflow Fixes
Codebase Cleanup
Engineering Discipline
Immediate Stabilization
Logic Extraction
Production Readiness
Project Boundaries
Repo Hygiene
Runtime Stability
Security & Config
State & Mutations
Structure Standardization
Testing
UX Trust
Workflow Continuity

## MSP Import
Outline Level | Summary | Task Name | Owner | Priority | Status | Start | Finish | Duration (days)
1 | Yes | Immediate Stabilization | 18 | 18 | 18 | 2026-03-30 | 2026-04-10 | 12
2 | No | Identify every duplicated module under src/<module> and src/components/<module> | Engineering | Critical | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Choose one canonical location for each duplicated file | Engineering | Critical | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Replace duplicate copies with imports/re-exports temporarily | Engineering | Critical | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Delete stale duplicate implementations after verification | Engineering | High | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Document final folder ownership rules | Engineering | High | Done | 2026-04-06 | 2026-04-10 | 5
1 | Yes | Broken Workflow Fixes | 18 | 18 | 18 | 2026-03-30 | 2026-04-03 | 5
2 | No | Confirm task creation no longer causes disappearing records | Engineering / QA | Critical | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Fix cost codes save behavior | Engineering | Critical | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Fix contracts save behavior | Engineering | Critical | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Fix change order edit behavior | Engineering | Critical | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Fix change order delete behavior | Engineering | Critical | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Fix checklist item behavior | Engineering | Critical | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Fix PMA nonfunctional paths | Engineering | Critical | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Audit drawing workflow pain points and list exact failures | Engineering / PM | High | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Verify SteelBuild-Pro sync reliability | Engineering | Critical | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Retest all corrected flows end to end | QA | Critical | Done | 2026-03-30 | 2026-04-03 | 5
1 | Yes | Runtime Stability | 18 | 18 | 18 | 2026-03-30 | 2026-04-10 | 12
2 | No | Find and fix remaining React hook-order violations | Engineering | Critical | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Review console errors and warnings across major pages | Engineering / QA | High | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Add loading, empty, and error states to critical modules | Engineering | High | In Progress | 2026-04-06 | 2026-04-10 | 5
2 | No | Add fallback handling for null project / null entity states | Engineering | High | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Verify modals and drawers do not break on missing data | QA | High | In Progress | 2026-04-06 | 2026-04-10 | 5
1 | Yes | Codebase Cleanup | 18 | 18 | 18 | 2026-04-06 | 2026-04-17 | 12
2 | No | Refactor src/pages/Submittals.jsx | Engineering | Critical | In Progress | 2026-04-06 | 2026-04-10 | 5
2 | No | Refactor src/pages/Constraints.jsx | Engineering | High | In Progress | 2026-04-13 | 2026-04-17 | 5
2 | No | Refactor src/pages/RFIs.jsx | Engineering | Critical | In Progress | 2026-04-06 | 2026-04-10 | 5
2 | No | Refactor src/pages/ResourceScheduling.jsx | Engineering | High | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Refactor src/Layout.jsx | Engineering | High | In Progress | 2026-04-13 | 2026-04-17 | 5
2 | No | Refactor src/pages/Deliveries.jsx | Engineering | High | In Progress | 2026-04-13 | 2026-04-17 | 5
2 | No | Refactor src/pages/Drawings.jsx | Engineering | Critical | In Progress | 2026-04-06 | 2026-04-10 | 5
1 | Yes | Repo Hygiene | 18 | 18 | 18 | 2026-04-06 | 2026-04-10 | 5
2 | No | Remove stale root-level duplicate folders | Engineering | High | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Remove old zip/tgz artifacts from repo workflow | Engineering | Medium | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Remove logs from tracked workspace | Engineering | Medium | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Remove or isolate dist from source repo workflow | Engineering | Medium | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Confirm .env.local is not exposed improperly | Engineering | Critical | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Update .gitignore if needed | Engineering | Medium | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Clean repo for multi-developer work | Engineering | High | Done | 2026-04-06 | 2026-04-10 | 5
1 | Yes | Structure Standardization | 18 | 18 | 18 | 2026-04-06 | 2026-04-17 | 12
2 | No | Define folder rules for pages/components/hooks/services/utils/entities | Engineering Lead | High | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Move shared UI to one shared location | Engineering | High | In Progress | 2026-04-13 | 2026-04-17 | 5
2 | No | Move workflow logic out of generic UI folders | Engineering | High | In Progress | 2026-04-13 | 2026-04-17 | 5
2 | No | Publish short architecture note for future edits | Engineering Lead | Medium | Done | 2026-04-13 | 2026-04-17 | 5
1 | Yes | Engineering Discipline | 18 | 18 | 18 | 2026-03-30 | 2026-04-24 | 26
2 | No | Confirm local lint script works consistently | Engineering | Critical | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Confirm local typecheck script works consistently | Engineering | Critical | Done | 2026-03-30 | 2026-04-03 | 5
2 | No | Fix highest-risk lint errors first | Engineering | High | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Fix unused imports and dead code | Engineering | Medium | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Fix prop/type/state issues in critical workflows first | Engineering | Critical | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Expand type coverage to src/lib, src/api, and src/components/ui | Engineering | High | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Stop excluding important folders from type validation | Engineering | High | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Add lint/typecheck to PR workflow or CI | Engineering | High | Done | 2026-04-20 | 2026-04-24 | 5
1 | Yes | State & Mutations | 18 | 18 | 18 | 2026-04-13 | 2026-04-24 | 12
2 | No | Create one standard pattern for fetch + transform + save | Engineering | High | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Create one standard pattern for mutation success/error toasts | Engineering | Medium | In Progress | 2026-04-13 | 2026-04-17 | 5
2 | No | Create one standard pattern for reload/refetch after save | Engineering | High | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Eliminate page-local ad hoc mutation logic | Engineering | High | In Progress | 2026-04-20 | 2026-04-24 | 5
2 | No | Review optimistic update behavior for reliability | Engineering | High | In Progress | 2026-04-20 | 2026-04-24 | 5
2 | No | Ensure state cannot silently drift from backend truth | Engineering | Critical | In Progress | 2026-04-20 | 2026-04-24 | 5
1 | Yes | Logic Extraction | 18 | 18 | 18 | 2026-04-13 | 2026-04-24 | 12
2 | No | Extract KPI calculations into utilities/services | Engineering | High | In Progress | 2026-04-13 | 2026-04-17 | 5
2 | No | Extract entity transformation logic into shared helpers | Engineering | High | In Progress | 2026-04-13 | 2026-04-17 | 5
2 | No | Extract project-context gating into reusable guards | Engineering | High | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Extract repeated badge/status formatting logic | Engineering | Medium | In Progress | 2026-04-20 | 2026-04-24 | 5
2 | No | Reduce major pages to layout + composition | Engineering | High | In Progress | 2026-04-20 | 2026-04-24 | 5
1 | Yes | Security & Config | 18 | 18 | 18 | 2026-04-06 | 2026-04-17 | 12
2 | No | Review src/api/base44Client.js | Engineering | Critical | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Review src/lib/app-params.js | Engineering | Critical | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Eliminate unsafe token sourcing from URL where possible | Engineering | Critical | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Reduce reliance on localStorage for sensitive auth flows | Engineering | High | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Replace loose requiresAuth: false patterns where inappropriate | Engineering | Critical | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Ensure business-critical paths require authenticated context | Engineering | Critical | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Verify project-level access boundaries are enforced | Engineering / QA | Critical | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Document approved auth/config pattern | Engineering Lead | Medium | Done | 2026-04-13 | 2026-04-17 | 5
1 | Yes | Backend Hardening | 18 | 18 | 18 | 2026-04-13 | 2026-04-24 | 12
2 | No | Review backend functions for auth consistency | Engineering | Critical | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Review unsafe service-role usage | Engineering | Critical | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Confirm project-level checks for sensitive operations | Engineering | Critical | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Validate webhook signature checks where applicable | Engineering | High | Done | 2026-04-20 | 2026-04-24 | 5
2 | No | Confirm environment variable names and usage are correct | Engineering | High | Done | 2026-04-13 | 2026-04-17 | 5
1 | Yes | UX Trust | 18 | 18 | 18 | 2026-04-06 | 2026-04-17 | 12
2 | No | Find all 'coming soon' or placeholder operational screens | PM / QA | High | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Hide incomplete features from production users | Engineering | High | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Replace placeholders with clear 'not enabled' messaging | Engineering | Medium | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Remove fake buttons or dead controls | Engineering | High | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Ensure every visible feature does something trustworthy | QA | Critical | In Progress | 2026-04-13 | 2026-04-17 | 5
1 | Yes | Workflow Continuity | 18 | 18 | 18 | 2026-04-06 | 2026-04-24 | 19
2 | No | Audit drawings workflow end to end | PM / QA / Engineering | Critical | Done | 2026-04-06 | 2026-04-10 | 5
2 | No | Audit RFI workflow end to end | PM / QA / Engineering | Critical | In Progress | 2026-04-06 | 2026-04-10 | 5
2 | No | Audit work package workflow end to end | PM / QA / Engineering | High | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Audit deliveries workflow end to end | PM / QA / Engineering | High | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Audit schedule workflow and look-ahead planning | PM / QA / Engineering | High | In Progress | 2026-04-13 | 2026-04-17 | 5
2 | No | Audit cost / SOV / budget control workflow | PM / QA / Engineering | Critical | In Progress | 2026-04-13 | 2026-04-17 | 5
2 | No | Audit PMA usefulness inside real PM workflow | PM / QA / Engineering | Critical | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Fix handoff gaps between office, shop, and field surfaces | Engineering | High | In Progress | 2026-04-20 | 2026-04-24 | 5
1 | Yes | Project Boundaries | 18 | 18 | 18 | 2026-04-13 | 2026-04-24 | 12
2 | No | Verify every operational module respects project context | Engineering / QA | Critical | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Remove silent cross-project blending in working modules | Engineering | High | Done | 2026-04-13 | 2026-04-17 | 5
2 | No | Separate executive roll-up views from project execution views | Engineering | High | Done | 2026-04-20 | 2026-04-24 | 5
2 | No | Confirm filters, summaries, and KPIs are scoped correctly | QA | High | In Progress | 2026-04-20 | 2026-04-24 | 5
2 | No | Retest project switching across major pages | QA | Critical | In Progress | 2026-04-20 | 2026-04-24 | 5
1 | Yes | Testing | 18 | 18 | 18 | 2026-04-20 | 2026-04-24 | 5
2 | No | Create tests for create/edit/delete on core records | QA / Engineering | Critical | Done | 2026-04-20 | 2026-04-24 | 5
2 | No | Add tests for task persistence | QA / Engineering | Critical | Done | 2026-04-20 | 2026-04-24 | 5
2 | No | Add tests for project context switching | QA / Engineering | High | Done | 2026-04-20 | 2026-04-24 | 5
2 | No | Add tests for stage advancement | QA / Engineering | High | Done | 2026-04-20 | 2026-04-24 | 5
2 | No | Add tests for assignment flows | QA / Engineering | Medium | In Progress | 2026-04-20 | 2026-04-24 | 5
2 | No | Add tests for cost calculations and KPIs | QA / Engineering | Critical | Done | 2026-04-20 | 2026-04-24 | 5
2 | No | Add tests for sync-sensitive workflows | QA / Engineering | Critical | Done | 2026-04-20 | 2026-04-24 | 5
2 | No | Add tests for drawing revision logic | QA / Engineering | Critical | Done | 2026-04-20 | 2026-04-24 | 5
2 | No | Add tests for major save forms | QA / Engineering | High | Done | 2026-04-20 | 2026-04-24 | 5
2 | No | Add tests for permission-sensitive operations | QA / Engineering | High | Done | 2026-04-20 | 2026-04-24 | 5
1 | Yes | Production Readiness | 18 | 18 | 18 | 2026-04-27 | 2026-05-01 | 5
2 | No | Re-audit all critical modules after refactors | QA / PM | High | Done | 2026-04-27 | 2026-05-01 | 5
2 | No | Re-run lint with zero critical issues | Engineering | High | Done | 2026-04-27 | 2026-05-01 | 5
2 | No | Re-run typecheck with expanded coverage | Engineering | High | Done | 2026-04-27 | 2026-05-01 | 5
2 | No | Re-test all core workflows | QA | Critical | Blocked | 2026-04-27 | 2026-05-01 | 5
2 | No | Re-check permissions and auth | QA / Engineering | Critical | Done | 2026-04-27 | 2026-05-01 | 5
2 | No | Re-check project boundary enforcement | QA | High | Done | 2026-04-27 | 2026-05-01 | 5
2 | No | Re-check UI trust and silent failure risk | QA / PM | High | Done | 2026-04-27 | 2026-05-01 | 5

## Notes
Usage
Excel:
Use the Tracker sheet as the working checklist.
Microsoft Project:
Use the companion XML file in this deliverable for direct import into Microsoft Project.
The MSP Import sheet mirrors the same task hierarchy and dates for quick reference.
Scheduling assumptions:
Plan start = Mar 30, 2026.
Week 1..5 map to Monday-start / Friday-target weekly buckets.
Each detailed task is set to a 5-day window for import simplicity.
Status update — July 23, 2026
Only tasks with direct GitHub PR, test, CI, or runbook evidence were marked Done. Broad security, workflow, project-boundary, backup/recovery, and full end-to-end readiness items remain open until their complete acceptance criteria are proven.