## Cover
STEELBUILD PRO
Structural Steel Project Management · Excel Edition
JOB 25531 · Skyport at Redfield
CLIENT | Westone |  |  | GENERAL CONTRACTOR | LGE Design/Build
ENGINEER OF RECORD | Khran |  |  | PROJECT MANAGER | Nick Lortz
SUPERINTENDENT | Matt Barbee |  |  | JOB TYPE | Beams/Joists/Deck
CONTRACT TYPE | Lump Sum |  |  | ADDRESS | 7600 E Redfield Rd. Scottsdale, AZ 85260
SNAPSHOT AT A GLANCE
Fabrication | $1,895,403 |  | 2026-10-01 | 162 | 4 | 21.2
PHASE | CONTRACT VALUE |  | FORECAST FINISH | DRAWING SHEETS | OPEN RFIS | TONS DELIVERED
On Track | Retainage 10% |  | Target 2026-12-31 | 129 released | of 59 total | 13 loads
WORKBOOK CONTENTS · click to open
▸ Command Center |  | Portfolio KPIs, ball-in-court & exceptions
▸ Detailing Hub |  | The moat — drawing sets ↔ submittals ↔ RFIs
▸ Drawing Sets |  | 13 packages tracked to set-level approval
▸ Drawings |  | 162 sheets with stage & revision
▸ Submittals |  | Shop-drawing workflow (IFA→OFA→BFA→OFS→IFC→RFF)
▸ RFIs |  | 59 requests for information w/ cost & schedule impact
▸ Schedule |  | 72 WBS tasks across the project phases
▸ Work Packages |  | Released work scoped by area & crew
▸ Deliveries |  | Truckloads, pieces & tonnage
▸ Fabrication |  | Fab-release control (module structure)
▸ Change Orders |  | Contract changes & margin
▸ Financials |  | Contract value, change orders & AIA pay-app
▸ Vendors |  | Subs, suppliers & service providers
▸ About |  | What SteelBuild Pro is + legends & data dictionary
Real-data snapshot generated June 22, 2026 · Source: SteelBuild Pro (live Supabase database) · Read-only demonstration workbook
SteelBuild Pro is a SaaS platform for structural steel fabricators & erectors. This workbook recreates its modules, one sheet per screen.

## Command Center
Command Center
Job 25531 · Skyport at Redfield · live operational rollups
KEY PERFORMANCE INDICATORS
162 | 13 |  | 13 |  | 4 |  | 1
DRAWING SHEETS | DRAWING SETS |  | SUBMITTALS |  | OPEN RFIS |  | RFIS · COST IMPACT
129 released | 0 approved |  | 7 released to fab |  | 59 total |  | flagged $
8 | 21.2 |  | 43% |  | 15 |  | 1
RFIS · SCHED IMPACT | TONS DELIVERED |  | SCHEDULE % COMPLETE |  | WORK PACKAGES |  | DELAYED TASKS
flagged days | 13 loads |  | 72 tasks |  | 61% avg |  | need attention
SUBMITTAL STATUS · shop-drawing workflow
Submitted / In For Approval |  |  |  | 1
Approved as Noted | [6 empty] | 5
Released for Fabrication | [7 empty] | 7
BALL IN COURT (open items) |  |  |  | EXCEPTIONS · what needs attention
Detailer |  | 6 |  | In review |  | S-003 Ladders - Bldg. 1 & 2 → EOR
GC |  | 4 |  | Open RFI |  | RFI #032 Stair 2 Tread, Mid-Landing Arrangement & Guardrail Clarification → GC
— |  | 3 |  | Open RFI |  | RFI #048 Regarding main steel BFA post review query of building-1 → GC
S&H |  | 2 |  | Open RFI |  | RFI #053 Door Jamb Post Install → GC
EOR |  | 1 |  | Open RFI · sched |  | RFI #060 Regarding hangar door post brace support arrangement at building-2. → GC
Owner |  | 1 |  | Delayed task |  | Ladders - Bldg. 1 & 2 → Detailing

## Detailing Hub
Detailing Control Center
The moat — drawing sets ↔ submittals ↔ RFIs, the way the real Hub links them
SET ↔ SUBMITTAL LINKAGE (auto-lock fires when the submittal is approved)
Drawing Set | Discipline | Rev | Sheets | Set Approval | Locked | Submittal | Submittal Status | Ball in Court
Panel Embeds - Bldg. 2 | Structural | A | 37 | Approved | ✓ | S-011 | Approved as Noted | Detailer
Balcony Rail - Bldg. 1 | Structural | A | 2 | Approved | ✓ | S-011 | Approved as Noted | Detailer
Stairs - Bldg 1 | Misc Metals | A | 13 | Approved | ✓ | S-004 | Approved as Noted | Detailer
Main Steel - Bldg. 2 | Structural | A | 24 | Approved | ✓ | S-009 | Released for Fabrication | Detailer
Balcony Rail - Bldg. 2 | Misc Metals | A | 11 | Approved | ✓ | S-001 | Approved as Noted | Detailer
Site Misc. Steel | Misc Metals | A | 13 | Approved | ✓ | S-002 | Approved as Noted | Detailer
Anchor Bolts - Bldg. 1 & 2 | Structural | 1 | 13 | Approved | ✓ | S-006 | Released for Fabrication | S&H
Ladders - Bldg. 1 & 2 | Misc Metals | A | 4
Stairs - Bldg. 2 | Misc Metals | A | 6 | Approved | ✓ | S-005 | Approved as Noted | Detailer
Panel Embeds - Bldg. 1 | Structural | 1 | 17 | Approved | ✓ | S-007 | Released for Fabrication
Main Steel - Bldg. 1 | Structural | 1 | 12 | Pending review | ✓ | S-010 | Released for Fabrication
Wedge Canopy Mockups | Misc Metals | A | 3 | Approved
Joists & Deck | Structural | 1 | 6 | Pending review | ✓ | S-012 | Released for Fabrication | Owner
OPEN RFIs AFFECTING DETAILING
RFI # | Subject | Status | Ball in Court | Sched | Assigned
RFI #032 | Stair 2 Tread, Mid-Landing Arrangement & Guardrail Clarification | Incomplete Response | GC |  | LGE
RFI #048 | Regarding main steel BFA post review query of building-1 | Incomplete Response | GC |  | LGE
RFI #053 | Door Jamb Post Install | Under Review | GC |  | LGE
RFI #060 | Regarding hangar door post brace support arrangement at building-2. | Under Review | GC | ✓ | LGE

## Drawing Sets
Drawing Sets
13 packages · tracked at the set level, not the sheet
Set Name | Discipline | Rev | Status | Approval | Locked | Sheets | Issued | Lock Reason
Panel Embeds - Bldg. 2 | Structural | A | Active | Approved | ✓ | 37 | 2026-03-13 | Auto-locked: submittal S-011 reached "Approved as Noted"
Balcony Rail - Bldg. 1 | Structural | A | Active | Approved | ✓ | 2 | 2026-03-23 | Auto-locked: submittal S-011 reached "Approved as Noted"
Stairs - Bldg 1 | Misc Metals | A | Active | Approved | ✓ | 13 | 2026-03-23 | Auto-locked: submittal S-004 reached "Approved as Noted"
Main Steel - Bldg. 2 | Structural | A | Active | Approved | ✓ | 24 | 2026-03-31 | Auto-locked: submittal S-009 reached "Released for Fabrication"
Balcony Rail - Bldg. 2 | Misc Metals | A | Active | Approved | ✓ | 11 | 2026-03-31 | Auto-locked: submittal S-001 reached "Approved as Noted"
Site Misc. Steel | Misc Metals | A | Active | Approved | ✓ | 13 | 2026-03-31 | Auto-locked: submittal S-002 reached "Approved as Noted"
Anchor Bolts - Bldg. 1 & 2 | Structural | 1 | Active | Approved | ✓ | 13 | 2026-04-02 | Auto-locked: submittal S-006 reached "Released for Fabrication"
Ladders - Bldg. 1 & 2 | Misc Metals | A | Active |  |  | 4 | 2026-04-08
Stairs - Bldg. 2 | Misc Metals | A | Active | Approved | ✓ | 6 | 2026-04-08 | Auto-locked: submittal S-005 reached "Approved as Noted"
Panel Embeds - Bldg. 1 | Structural | 1 | Active | Approved | ✓ | 17 | 2026-05-11 | Auto-locked: submittal S-007 reached "Released for Fabrication"
Main Steel - Bldg. 1 | Structural | 1 | Active | Pending review | ✓ | 12 | 2026-05-20 | Auto-locked: submittal S-010 reached "Released for Fabrication"
Wedge Canopy Mockups | Misc Metals | A | Active | Approved |  | 3 | 2026-05-27
Joists & Deck | Structural | 1 | Active | Pending review | ✓ | 6 | 2026-06-18 | Auto-locked: submittal S-012 reached "Released for Fabrication"

## Drawings
Drawings
162 sheets · 129 released for fabrication
Sheet # | Title | Discipline | Rev | Stage | Drawing Set | Submitted | Returned | Superseded | RFIs
101ABP101 | ANCHOR BOLT LAYOUT PLAN @ BLDG.1 | Structural | 1 | Released | Anchor Bolts - Bldg. 1 & 2 | 2026-02-24 | 2026-04-02 | No | 0
101E101 | ISOMETRIC VIEW @ BLDG.1 | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E102 | PARTIAL EMBED LAYOUT PLAN | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E103 | PARTIAL EMBED LAYOUT PLAN @ BLDG.1 | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E104 | ELEVATION | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E105 | ELEVATION @ BLDG.1 | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E106 | ELEVATION @ BLDG.1 | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E107 | ELEVATION | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E108 | ELEVATION | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E109 | ELEVATION | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E110 | ELEVATION @ BLDG.1 | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E111 | ELEVATION | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E112 | ELEVATION | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E113 | ELEVATION | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E114 | ELEVATION | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E115 | ELEVATION | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E153 | PANEL EMBED MISC.ELEVATION @ BLDG.1 | Structural | 1 | Released | Panel Embeds - Bldg. 1 | 2026-03-02 | 2026-03-25 | No | 0
101E155 | EMBED MISC DETAIL & SECTION @ BLDG.1 | Misc Metals | A | Released | Panel Embeds - Bldg. 1 | 2026-03-31 | 2026-05-26 | No | 0
102ABP101 | PARTIAL ANCHOR BOLT LAYOUT PLAN @ BLDG.2 | Structural | 1 | Released | Anchor Bolts - Bldg. 1 & 2 | 2026-02-24 | 2026-04-02 | No | 0
102ABP102 | PARTIAL ANCHOR BOLT LAYOUT PLAN @ BLDG.2 | Structural | 1 | Released | Anchor Bolts - Bldg. 1 & 2 | 2026-02-24 | 2026-04-02 | No | 0
102ABP103 | PARTIAL ANCHOR BOLT LAYOUT PLAN @ BLDG.2 | Structural | 1 | Released | Anchor Bolts - Bldg. 1 & 2 | 2026-02-24 | 2026-04-02 | No | 0
102ABP104 | DETAIL & SECTION @ BLDG.2 | Structural | 1 | Released | Anchor Bolts - Bldg. 1 & 2 | 2026-02-24 | 2026-04-02 | No | 0
102ABP105 | DETAIL & SECTION @ BLDG.2 | Structural | 1 | Released | Anchor Bolts - Bldg. 1 & 2 | 2026-02-24 | 2026-04-02 | No | 0
102E101 | ISOMETRIC VIEW @ BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E102 | PARTIAL PANEL EMBED LAYOUT PLAN @BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E103 | PARTIAL PANEL EMBED LAYOUT PLAN @BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E104 | ELEVATION @ BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E105 | ELEVATION @ BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E106 | ELEVATION @ BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E107 | ELEVATION @ BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E108 | ELEVATION @ BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E109 | ELEVATION @ BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E111 | PANEL ELEVATION @ GRID LINE - H | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E112 | PANEL ELEVATION @ GRID LINE - I | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E113 | PANEL ELEVATION @ GRID LINE - J | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E114 | PANEL ELEVATION @ GRID LINE - K | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E115 | PANEL ELEVATION @ GRID LINE - L | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E116 | PANEL ELEVATION @ GRID LINE - M | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E117 | PANEL ELEVATION @ GRID LINE - N | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E118 | PANEL ELEVATION @ GRID LINE - O | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E119 | PANEL ELEVATION @ GRID LINE - P | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E120 | PANEL ELEVATION @ GRID LINE - Q | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E121 | PANEL ELEVATION @ GRID LINE - R | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E122 | PANEL ELEVATION @ GRID LINE - S | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E123 | PANEL ELEVATION @ GRID LINE - T | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E124 | PANEL ELEVATION @ GRID LINE - U | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E125 | PANEL ELEVATION @ GRID LINE - V | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E126 | PANEL ELEVATION @ GRID LINE - W | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E127 | PANEL ELEVATION @ GRID LINE - X | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E128 | PANEL ELEVATION @ GRID LINE - Y | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E129 | PANEL ELEVATION @ GRID LINE - Z | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E130 | PANEL ELEVATION @ GRID LINE - AA | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E151 | PARTIAL PANEL EMBED MISC. LAYOUT PLAN@BLDG 2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E152 | PARTIAL PANEL EMBED MISC. LAYOUT PLAN@BLDG 2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E153 | PANEL EMBED MISC.ELEVATION @ BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E154 | PANEL EMBED MISC.ELEVATION @ BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E155 | PANEL EMBED MISC.ELEVATION @ BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E156 | PANEL EMBED MISC.ELEVATION @ BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E157 | PANEL EMBED MISC.ELEVATION @ BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102E158 | EMBED MISC DETAIL & SECTION @ BLDG.2 | Misc Metals | 1 | Released | Panel Embeds - Bldg. 2 | 2026-03-23 | 2026-05-11 | No | 0
102TP101 | TEMPLATE | Structural | 1 | Released | Anchor Bolts - Bldg. 1 & 2 | 2026-02-24 | 2026-04-02 | No | 0
102TP102 | TEMPLATE | Structural | 1 | Released | Anchor Bolts - Bldg. 1 & 2 | 2026-02-24 | 2026-04-02 | No | 0
102TP103 | TEMPLATE | Structural | 1 | Released | Anchor Bolts - Bldg. 1 & 2 | 2026-02-24 | 2026-04-02 | No | 0
102TP104 | TEMPLATE | Structural | 1 | Released | Anchor Bolts - Bldg. 1 & 2 | 2026-02-24 | 2026-04-02 | No | 0
102TP105 | TEMPLATE | Structural | 1 | Released | Anchor Bolts - Bldg. 1 & 2 | 2026-02-24 | 2026-04-02 | No | 0
102TP106 | TEMPLATE | Structural | 1 | Released | Anchor Bolts - Bldg. 1 & 2 | 2026-02-24 | 2026-04-02 | No | 0
102TP107 | TEMPLATE | Structural | 1 | OFS | Anchor Bolts - Bldg. 1 & 2 | 2026-02-24 | 2026-04-02 | No | 0
501E101 | PARTIAL MAIN STEEL FRAMING PLAN @ BLDG.1 | Structural | 1 | Released | Main Steel - Bldg. 1 | 2026-03-31 | 2026-04-09 | No | 0
501E102 | PARTIAL MAIN STEEL FRAMING PLAN @ BLDG.1 | Structural | 1 | Released | Main Steel - Bldg. 1 | 2026-03-31 | 2026-04-09 | No | 0
501E103 | PARTIAL MAIN STEEL FRAMING PLAN @ BLDG.1 | Structural | 1 | Released | Main Steel - Bldg. 1 | 2026-03-31 | 2026-04-09 | No | 0
501E109 | DETAILS AND SECTION @ BLDG.1 | Structural | 1 | Released | Main Steel - Bldg. 1 | 2026-03-31 | 2026-04-09 | No | 0
501E110 | DETAILS AND SECTION @ BLDG.1 | Structural | 1 | Released | Main Steel - Bldg. 1 | 2026-03-31 | 2026-04-09 | No | 0
501E111 | DETAILS AND SECTION @ BLDG.1 | Structural | 1 | Released | Main Steel - Bldg. 1 | 2026-03-31 | 2026-04-09 | No | 0
501E151 | WEDGE CANOPY ISOMETRIC VIEW | Misc Metals | A | Released | Wedge Canopy Mockups |  |  | No | 0
501E152 | WEDGE CANOPY FRAMING PLANS @ BLDG.1 | Misc Metals | A | Released | Wedge Canopy Mockups |  |  | No | 0
501E155 | ISOMETRIC DETAILS @ CORNER | Misc Metals | A | Released | Wedge Canopy Mockups |  |  | No | 0
502E101 | PARTIAL MAIN STEEL FRAMING PLAN@BLDG_2 | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E102 | PARTIAL MAIN STEEL FRAMING PLAN@BLDG_2 | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E103 | PARTIAL MAIN STEEL FRAMING PLAN@BLDG_2 | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E104 | PARTIAL MAIN STEEL FRAMING PLAN@BLDG_2 | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E105 | PARTIAL MAIN STEEL FRAMING PLAN@BLDG_2 | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E106 | PARTIAL MAIN STEEL FRAMING PLAN@BLDG_2 | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E107 | PARTIAL MAIN STEEL FRAMING PLAN@BLDG-2 | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E108 | PARTIAL MAIN STEEL FRAMING PLAN@BLDG-2 | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E109 | PARTIAL MAIN STEEL FRAMING PLAN@BLDG-2 | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E110 | WEDGE CANOPY FRAMING PLAN@BLDG-2 | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E111 | WEDGE CANOPY FRAMING PLAN@BLDG-2 | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E112 | WEDGE CANOPY FRAMING PLAN@BLDG-2 | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E113 | WEDGE CANOPY FRAMING PLAN@BLDG-2 | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E114 | MAIN STEEL DETAILS AND SECTION | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E115 | MAIN STEEL DETAILS AND SECTION | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E116 | MAIN STEEL DETAILS AND SECTION | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E117 | MAIN STEEL DETAILS AND SECTION | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E118 | MAIN STEEL DETAILS AND SECTION | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E119 | MAIN STEEL DETAILS AND SECTION | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E120 | MAIN STEEL DETAILS AND SECTION | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E121 | MAIN STEEL DETAILS AND SECTION | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E122 | MAIN STEEL DETAILS AND SECTION | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E123 | WEGDE CANOPY DETAILS AND SECTION | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-05-14 | No | 0
502E124 | WEGDE CANOPY DETAILS AND SECTION | Structural | 1 | Released | Main Steel - Bldg. 2 | 2026-03-31 | 2026-04-09 | No | 0
601E101 | STAIR-1 LAYOUT PLAN @ BLDG.1 | Misc Metals | A | OFS | Stairs - Bldg 1 | 2026-03-23 | 2026-05-11 | No | 0
601E102 | ELEVATIONS & SECTION | Misc Metals | A | OFS | Stairs - Bldg 1 | 2026-03-23 | 2026-05-11 | No | 0
601E103 | ELEVATIONS | Misc Metals | A | OFS | Stairs - Bldg 1 | 2026-03-23 | 2026-05-11 | No | 0
601E104 | ELEVATIONS & SECTIONS | Misc Metals | A | OFS | Stairs - Bldg 1 | 2026-03-23 | 2026-05-11 | No | 0
601E105 | DETAIL & SECTIONS | Misc Metals | A | OFS | Stairs - Bldg 1 | 2026-03-23 | 2026-05-11 | No | 0
601E1051 | SS CABLE RAIL FITTING | Misc Metals | A | OFS | Stairs - Bldg 1 | 2026-03-23 | 2026-05-11 | No | 0
601E1052 | SS CABLE RAIL FITTING @ BALCONY | Misc Metals | A | OFS | Balcony Rail - Bldg. 1 | 2026-03-23 | 2026-06-11 | No | 0
601E108 | STAIR-2 DETAILS | Misc Metals | A | OFS | Stairs - Bldg 1 | 2026-03-23 | 2026-05-11 | No | 0
601E111 | STAIR-2 LAYOUT PLAN @ BLDG.1 | Misc Metals | A | OFS | Stairs - Bldg 1 | 2026-03-23 | 2026-05-11 | No | 0
601E112 | ELEVATIONS | Misc Metals | A | OFS | Stairs - Bldg 1 | 2026-03-23 | 2026-05-11 | No | 0
601E114 | ELEVATIONS | Misc Metals | A | OFS | Stairs - Bldg 1 | 2026-03-23 | 2026-05-11 | No | 0
601E115 | ELEVATIONS | Misc Metals | A | OFS | Stairs - Bldg 1 | 2026-03-23 | 2026-05-11 | No | 0
601E116 | DETAILS & SECTIONS | Misc Metals | A | OFS | Stairs - Bldg 1 | 2026-03-23 | 2026-05-11 | No | 0
601E117 | DETAILS & SECTIONS | Misc Metals | A | OFS | Stairs - Bldg 1 | 2026-03-23 | 2026-05-11 | No | 0
601E121 | ROOF ACCESS LADDER LAYOUT PLAN | Misc Metals | A | Released | Ladders - Bldg. 1 & 2 | 2026-04-08 |  | No | 0
601E123 | BALCONY GUARDRAIL LAYOUT PLAN | Misc Metals | A | OFS | Balcony Rail - Bldg. 1 | 2026-03-23 | 2026-06-11 | No | 0
602E103 | STAIR-2 LAYOUT PLAN | Misc Metals | A | OFS | Stairs - Bldg. 2 | 2026-04-08 | 2026-05-11 | No | 0
602E104 | STAIR-3 LAYOUT PLAN | Misc Metals | A | OFS | Stairs - Bldg. 2 | 2026-04-08 | 2026-05-11 | No | 0
602E105 | CABLE RAIL & END FITTING TABLE | Misc Metals | A | OFS | Stairs - Bldg. 2 | 2026-04-08 | 2026-05-11 | No | 0
602E1051 | SS CABLE RAIL FITTING @ BALCONY | Misc Metals | A | OFS | Balcony Rail - Bldg. 2 | 2026-03-23 | 2026-06-09 | No | 0
602E121 | BALCONY GUARDRAIL LAYOUT PLAN | Misc Metals | A | OFS | Balcony Rail - Bldg. 2 | 2026-03-23 | 2026-06-09 | No | 0
602E122 | BALCONY GUARDRAIL LAYOUT PLAN | Misc Metals | A | OFS | Balcony Rail - Bldg. 2 | 2026-03-23 | 2026-06-09 | No | 0
602E123 | BALCONY GUARDRAIL LAYOUT PLAN | Misc Metals | A | OFS | Balcony Rail - Bldg. 2 | 2026-03-23 | 2026-06-09 | No | 0
602E124 | BALCONY GUARDRAIL LAYOUT PLAN | Misc Metals | A | OFS | Balcony Rail - Bldg. 2 | 2026-03-23 | 2026-06-09 | No | 0
602E125 | ROOF ACCESS LADDER LAYOUT PLAN @BLDG.2 | Misc Metals | A | Released | Ladders - Bldg. 1 & 2 | 2026-04-08 |  | No | 0
602E126 | ROOF ACCESS LADDER LAYOUT PLAN @BLDG.2 | Misc Metals | A | Released | Ladders - Bldg. 1 & 2 | 2026-04-08 |  | No | 0
602E128 | ROOF ACCESS LADDER LAYOUT PLAN @BLDG.2 | Misc Metals | A | Released | Ladders - Bldg. 1 & 2 | 2026-04-08 |  | No | 0
602E151 | STAIR-2 ELEVATION | Misc Metals | A | OFS | Stairs - Bldg. 2 | 2026-04-08 | 2026-05-11 | No | 0
602E152 | STAIR-3 ELEVATION | Misc Metals | A | OFS | Stairs - Bldg. 2 | 2026-04-08 | 2026-05-11 | No | 0
602E153 | STAIR-2 & STAIR-3 ELEVATION | Misc Metals | A | OFS | Stairs - Bldg. 2 | 2026-04-08 | 2026-05-11 | No | 0
602M103 | CABLE RAIL & END FITTING TABLE | Misc Metals | A | OFS | Balcony Rail - Bldg. 2 | 2026-03-23 | 2026-06-09 | No | 0
602M106 | CABLE RAIL & END FITTING TABLE | Misc Metals | A | OFS | Balcony Rail - Bldg. 2 | 2026-03-23 | 2026-06-09 | No | 0
602M107 | CABLE RAIL & END FITTING TABLE | Misc Metals | A | OFS | Balcony Rail - Bldg. 2 | 2026-03-23 | 2026-06-09 | No | 0
602M108 | CABLE RAIL & END FITTING TABLE | Misc Metals | A | OFS | Balcony Rail - Bldg. 2 | 2026-03-23 | 2026-06-09 | No | 0
602M110 | CABLE RAIL & END FITTING TABLE | Misc Metals | A | OFS | Balcony Rail - Bldg. 2 | 2026-03-23 | 2026-06-09 | No | 0
602M111 | CABLE RAIL & END FITTING TABLE | Misc Metals | A | OFS | Balcony Rail - Bldg. 2 | 2026-03-23 | 2026-06-09 | No | 0
701E101 | MISC. OVERALL PLAN | Misc Metals | A | Released | Site Misc. Steel | 2026-03-31 | 2026-05-26 | No | 0
701E102 | DOUBLE TRASH ENCLOSURE GATE PLAN @BLDG-1 | Misc Metals | A | Released | Site Misc. Steel | 2026-03-31 | 2026-05-26 | No | 0
701E103 | SINGLE TRASH ENCLOSURE GATE PLAN @ BLDG-2 | Misc Metals | A | Released | Site Misc. Steel | 2026-03-31 | 2026-05-26 | No | 0
701E104 | SECTION & DETAILS | Misc Metals | A | Released | Site Misc. Steel | 2026-03-31 | 2026-05-26 | No | 0
701E105 | ROLLING GATE ERECTION PLAN (WEST) @ BLDG.1 | Misc Metals | A | Released | Site Misc. Steel | 2026-03-31 | 2026-05-26 | No | 0
701E106 | ROLLING GATE ERECTION PLAN (EAST) @ BLDG.2 | Misc Metals | A | Released | Site Misc. Steel | 2026-03-31 | 2026-05-26 | No | 0
701E107 | SECTION & DETAIL | Misc Metals | A | Released | Site Misc. Steel | 2026-03-31 | 2026-05-26 | No | 0
701E108 | SITE BOLLARD LAYOUT PLAN @ BUILDING 2 | Misc Metals | A | Released | Site Misc. Steel | 2026-03-31 | 2026-05-26 | No | 0
701E109 | SCUPPER ERECTION PLAN | Misc Metals | A | Released | Site Misc. Steel | 2026-03-31 | 2026-05-26 | No | 0
701E110 | SAFETY ANCHOR POST PLAN @BLDG. 1 | Misc Metals | A | Released | Site Misc. Steel | 2026-03-31 | 2026-05-26 | No | 0
701E111 | PARTIAL SAFETY ANCHOR POST PLAN @BLDG. 2 | Misc Metals | A | Released | Site Misc. Steel | 2026-03-31 | 2026-05-26 | No | 0
701E112 | PARTIAL SAFETY ANCHOR POST PLAN @BLDG. 2 | Misc Metals | A | Released | Site Misc. Steel | 2026-03-31 | 2026-05-26 | No | 0
701E113 | PARTIAL SAFETY ANCHOR POST PLAN @BLDG. 2 | Misc Metals | A | Released | Site Misc. Steel | 2026-03-23 | 2026-05-11 | No | 0
D1.1 | ROOF DECK PLACEMENT PLAN | Structural | 1 | Released | Joists & Deck | 2026-04-06 | 2026-05-06 | No | 0
D1.2 | LOWER ROOF DECK PLACEMENT PLAN | Structural | 1 | Released | Joists & Deck | 2026-04-06 | 2026-05-06 | No | 0
D1.3 | SECOND FLOOR DECK PLACEMENT PLAN | Structural | 1 | Released | Joists & Deck | 2026-04-06 | 2026-05-06 | No | 0
D1.4 | UPPER ROOF DECK PLACEMENT PLAN | Structural | 1 | Released | Joists & Deck | 2026-04-06 | 2026-05-06 | No | 0
D1.5 | SECOND FLOOR DECK PLACEMENT PLAN (EAST) | Structural | 1 | Released | Joists & Deck | 2026-04-06 | 2026-05-06 | No | 0
D1.6 | STAIRS DECK PLACEMENT PLAN | Structural | 1 | Released | Joists & Deck | 2026-04-06 | 2026-05-06 | No | 0
D1.7 | LOWER ROOF DECK PLACEMENT PLAN (EAST) | Structural | 1 | Released | Joists & Deck | 2026-04-06 | 2026-05-06 | No | 0
J1.1 | ROOF JOIST PLACEMENT PLAN | Structural | 1 | Released | Joists & Deck | 2026-04-06 | 2026-05-06 | No | 0
J1.2 | LOWER ROOF JOIST PLACEMENT PLAN | Structural | 1 | Released | Joists & Deck | 2026-04-06 | 2026-05-06 | No | 0
J1.3 | SECOND FLOOR JOIST PLACEMENT PLAN | Structural | 1 | Released | Joists & Deck | 2026-04-06 | 2026-05-06 | No | 0
J1.4 | UPPER ROOF JOIST PLACEMENT PLAN | Structural | 1 | Released | Joists & Deck | 2026-04-06 | 2026-05-06 | No | 0
J1.5 | SECOND FLOOR JOIST PLACEMENT PLAN (EAST) | Structural | 1 | Released | Joists & Deck | 2026-04-06 | 2026-05-06 | No | 0
J1.6 | LOWER ROOF JOIST PLACEMENT PLAN (EAST) | Structural | 1 | Released | Joists & Deck | 2026-04-06 | 2026-05-06 | No | 0

## Submittals
Submittals
Shop-drawing workflow — Not Started → IFA → OFA → BFA → OFS → IFC → Released for Fab
STAGE LEGEND
IFA | In For Approval | OFA | Out For Approval | BFA | Back From Approval | OFS | Out For Scrub | IFC | Issued For Construction | R&R | Revise & Resubmit | RFF | Released for Fabrication
Sub # | Title | Spec | Discipline | Rev | Rnd | Status | Ball in Court | Reviewer | Submitted | Required | Returned
S-004 | Stairs - Bldg. 1 | 05 12 00 | Stairs & Rails | A | 1 | Approved as Noted | Detailer | LGE | 2026-03-23 | 2026-05-25 | 2026-05-11
S-002 | Site Misc. Steel - Bldg. 1 & 2 | 05 12 00 | Misc Metals | 1 | 1 | Approved as Noted | Detailer | Khran / Ware-Malcomb | 2026-03-31 | 2026-04-13
S-005 | Stairs - Bldg. 2 |  | Stairs & Rails | 1 | 1 | Approved as Noted | Detailer |  | 2026-04-08 | 2026-04-22
S-003 | Ladders - Bldg. 1 & 2 | 05 12 00 | Stairs & Rails | A | 1 | Submitted | EOR | Khran / Ware-Malcomb | 2026-04-08 | 2026-04-22
S-011 | Balcony Railing - Bldg. 1 | 05 12 00 | Stairs & Rails | 1 | 1 | Approved as Noted | Detailer |  | 2026-06-10 | 2026-06-24
S-001 | Balcony Railing - Bldg. 2 | 05 12 00 | Stairs & Rails | 1 | 1 | Approved as Noted | Detailer | Khran / Ware-Malcomb | 2026-06-11 | 2026-06-24
S-012 | Joists/Deck | 05 12 00 | Structural | 1 | 2 | Released for Fabrication | Owner | Khran / Ware-Malcomb | 2026-06-11 | 2026-06-19 | 2026-06-18
S-009 | Main Steel - Bldg. 2 | 05 12 00 | Structural | 1 | 1 | Released for Fabrication | Detailer | Khran / Ware-Malcomb | 2026-06-13
S-007 | Panel Embeds - Bldg. 1 |  | Embeds | 1 | 1 | Released for Fabrication |  |  | 2026-06-13
S-008 | Panel Embeds - Bldg. 2 |  | Embeds | 1 | 1 | Released for Fabrication |  |  | 2026-06-13
S-010 | Main Steel - Bldg. 1 | 05 12 00 | Structural | 2 | 2 | Released for Fabrication |  | Khran / Ware-Malcomb | 2026-06-13
S-006 | Anchor Bolts - Bldg. 1 & 2 | 05 12 00 | Anchor Bolts | 1 | 1 | Released for Fabrication | S&H | Khran / Ware-Malcomb | 2026-06-13
S-015 | Wedge Canopy Mockups | 05 12 00 | Mock Up | 1 | 1 | Released for Fabrication | S&H | LGE | 2026-06-15 | 2026-06-15

## RFIs
RFIs
59 requests · 4 open · 1 cost-impact · 8 schedule-impact
RFI # | Subject | Discipline | Status | Priority | Ball | Assigned | Submitted | Answered | Cost | Sched | Question | Answer
RFI #001 | 2025.12.12) - Gridline Conflict - |  | Closed | Medium | GC | LGE | 2025-12-12 | 2025-12-12 |  | ✓ | 2025.12.12) - Gridline Conflict -
RFI #002 | 2025.12.12) - Column Information Conflict - |  | Closed | Medium | GC | LGE | 2025-12-12 | 2025-12-12 |  |  | 2025.12.12) - Column Information Conflict -
RFI #003 | Roof Slope at Bldg. 1 & 2 |  | Closed | Medium | GC | LGE | 2025-12-18 | 2026-02-11 |  |  | Roof Slope at Bldg. 1 & 2
RFI #004 | Panel thickness at the building-1 |  | Closed | Medium | GC | LGE | 2025-12-18 | 2026-02-11 |  |  | Panel thickness at the building-1
RFI #005 | Beam to Column Moment Connection Requirement in Building 1 |  | Closed | Medium | GC | LGE | 2025-12-18 | 2026-02-11 |  |  | Beam to Column Moment Connection Requirement in Building 1
RFI #006 | Stair 1 Wall Layout at Bldg. 1 |  | Closed | Medium | GC | LGE | 2025-12-18 | 2026-03-23 |  |  | Stair 1 Wall Layout at Bldg. 1
RFI #007 | Beam Splice Connection Requirement in Bldg. 1 & 2 |  | Closed | Medium | GC | LGE | 2025-12-18 | 2026-02-11 |  |  | Beam Splice Connection Requirement in Bldg. 1 & 2
RFI #008 | Column Member Section Size at Bldg. 2 |  | Closed | Medium | GC | LGE | 2025-12-29 | 2026-01-18 |  |  | Column Member Section Size at Bldg. 2
RFI #009 | Column Origin at Bldg. 2 |  | Closed | Medium | GC | LGE | 2025-12-29 | 2026-01-18 |  |  | Column Origin at Bldg. 2
RFI #010 | Deatailed Layout of Stairs at Bldg. 2 |  | Closed | Medium | GC | LGE | 2025-12-29 | 2026-03-02 |  |  | Deatailed Layout of Stairs at Bldg. 2
RFI #011 | Door Opening and Platform Location |  | Closed | Medium | GC | LGE | 2025-12-31 | 2026-02-11 |  |  | Door Opening and Platform Location
RFI #012 | Steel Landing Length in Building 1 & 2 |  | Closed | Medium | GC | LGE | 2025-12-31 | 2026-05-21 |  |  | Steel Landing Length in Building 1 & 2
RFI #013 | Door Size and Elevation in Building 2 |  | Closed | Medium | GC | LGE | 2026-01-05 | 2026-02-11 |  |  | Door Size and Elevation in Building 2
RFI #014 | Ladder and Landing Support Building 1 & 2 | Structural | Closed | Medium | GC | LGE | 2026-01-06 | 2026-06-13 |  | ✓ | Ladder and Landing Support Building 1 & 2 | Please see attached
RFI #015 | Panel Hold Down Embed Building 1 & 2 |  | Closed | Medium | GC | LGE | 2026-01-13 | 2026-01-14 |  |  | Panel Hold Down Embed Building 1 & 2
RFI #016 | Panel Thickness & Embed Locations Building 1 & 2 |  | Closed | Medium | GC | LGE | 2026-01-13 | 2026-01-14 |  |  | Panel Thickness & Embed Locations Building 1 & 2
RFI #017 | Panel Gap & Joist Bearing Connection |  | Closed | Medium | GC | LGE | 2026-01-13 | 2026-01-14 |  |  | Panel Gap & Joist Bearing Connection
RFI #018 | Joist Seat Depth |  | Closed | Medium | GC | LGE | 2026-01-14 | 2026-01-16 |  |  | Joist Seat Depth
RFI #019 | Clear Width & Tread Arrangement |  | Closed | Medium | GC | LGE | 2026-01-14 | 2026-03-02 |  |  | Clear Width & Tread Arrangement
RFI #020 | Balcony & Stair Member Confirmation |  | Closed | Medium | GC | LGE | 2026-01-14 | 2026-01-18 |  |  | Balcony & Stair Member Confirmation
RFI #021 | Regarding canopy beams & their elvation at the office-4 area of building-2 |  | Closed | Medium | GC | LGE | 2026-02-01 | 2026-05-15 |  |  | Regarding canopy beams & their elvation at the office-4 area of building-2
RFI #022 | Door Height at Hangars - Bldg. 2 |  | Closed | Medium | GC | LGE | 2026-02-01 | 2026-02-01 |  |  | Door Height at Hangars - Bldg. 2
RFI #023 | Regarding stair column footing in both building 1 & 2 |  | Closed | Medium | GC | LGE | 2026-02-13 | 2026-03-02 |  |  | Regarding stair column footing in both building 1 & 2
RFI #024 | Missing beam embed detail at building-2 |  | Closed | Medium | GC | LGE | 2026-02-13 | 2026-05-15 |  |  | Missing beam embed detail at building-2
RFI #025 | Stair-3 stringer member section size at building-2 |  | Closed | Medium | GC | LGE | 2026-02-13 | 2026-03-23 |  |  | Stair-3 stringer member section size at building-2
RFI #026 | Embed stud length |  | Closed | Medium | GC | LGE | 2026-02-13 | 2026-02-19 |  |  | Embed stud length
RFI #027 | Bottom of deck elevations |  | Closed | Medium | GC | LGE | 2026-02-13 | 2026-05-15 |  |  | Bottom of deck elevations
RFI #028 | Door opening and platform location in building-2 |  | Closed | Medium | GC | LGE | 2026-02-13 | 2026-02-19 |  |  | Door opening and platform location in building-2
RFI #029 | Cable guardrail post material grade |  | Closed | Medium | GC | LGE | 2026-02-13 | 2026-05-06 |  |  | Cable guardrail post material grade
RFI #030 | Regarding Stair Requirement |  | Closed | Medium | GC | LGE | 2026-02-13 | 2026-03-02 |  |  | Regarding Stair Requirement
RFI #031 | Regarding joist bearing angle sizes, joist seat depth & missing joist depth |  | Closed | Medium | GC | LGE | 2026-02-17 | 2026-03-02 |  |  | Regarding joist bearing angle sizes, joist seat depth & missing joist depth
RFI #032 | Stair 2 Tread, Mid-Landing Arrangement & Guardrail Clarification | Misc Metals | Incomplete Response | Medium | GC | LGE | 2026-02-17 |  |  |  | Stair 2 Tread, Mid-Landing Arrangement & Guardrail Clarification
RFI #033 | Wedge Frame Connection |  | Closed | Medium | GC | LGE | 2026-02-19 | 2026-05-11 |  |  | Wedge Frame Connection
RFI #034 | Steel Column & Concrete Panel Footing Elevations |  | Closed | Medium | GC | LGE | 2026-02-25 | 2026-05-15 |  |  | Steel Column & Concrete Panel Footing Elevations
RFI #035 | Regarding DLH Joist Bearing Member Section Size |  | Closed | Medium | GC | LGE | 2026-02-25 | 2026-05-15 |  |  | Regarding DLH Joist Bearing Member Section Size
RFI #036 | Steel Column & Concrete. Panel Footing Elevation |  | Closed | Medium | GC | LGE | 2026-02-25 | 2026-03-04 |  |  | Steel Column & Concrete. Panel Footing Elevation
RFI #037 | Regarding Wedge Frame Support Requirement at Building 1 & 2 | Structural | Closed | Medium | GC | LGE | 2026-02-25 |  |  |  | Regarding Wedge Frame Support Requirement at Building 1 & 2
RFI #038 | Regarding Joist Bearing Connection at Building-2 |  | Closed | Medium | GC | LGE | 2026-03-02 | 2026-03-03 |  |  | Regarding Joist Bearing Connection at Building-2
RFI #039 | Joist Bearing Connection at Building 2 |  | Closed | Medium | GC | LGE | 2026-03-02 | 2026-03-20 |  |  | Joist Bearing Connection at Building 2
RFI #040 | Regarding Stair-3 mid-landing perimeter landing angle size at building-2 |  | Closed | Medium | GC | LGE | 2026-03-05 | 2026-05-11 |  |  | Regarding Stair-3 mid-landing perimeter landing angle size at building-2
RFI #041 | Regarding Anchor Bolt BFA Post Review Query of Both Building 1 & 2 |  | Closed | Medium | GC | LGE | 2026-03-10 | 2026-03-20 |  |  | Regarding Anchor Bolt BFA Post Review Query of Both Building 1 & 2
RFI #043 | Regarding adjustmentrotation of ledger,joist & beam embed at future panel opening |  | Closed | Medium | GC | LGE | 2026-03-10 | 2026-05-15 |  |  | Regarding adjustmentrotation of ledger,joist & beam embed at future panel opening
RFI #044 | Regarding Door Jamb & Door Guard Connections at Both Buildings 1 & 2 |  | Closed | Medium | GC | LGE | 2026-03-24 | 2026-05-06 |  |  | Regarding Door Jamb & Door Guard Connections at Both Buildings 1 & 2
RFI #045 | Grout Thickness of Section 5R03 of Footing Drawing |  | Closed | Medium | GC | LGE | 2026-04-03 | 2026-04-13 |  |  | Grout Thickness of Section 5R03 of Footing Drawing
RFI #046 | Ladder Mid-Landing at Hanger Building 1 & 2 - | Structural | Closed | Medium | GC | LGE | 2026-04-07 |  |  | ✓ | Ladder Mid-Landing at Hanger Building 1 & 2 -
RFI #047 | Regarding Panel embed & panel misc. BFA review query of building-2 |  | Closed | Medium | GC | LGE | 2026-04-10 | 2026-05-08 |  |  | Regarding Panel embed & panel misc. BFA review query of building-2
RFI #048 | Regarding main steel BFA post review query of building-1 | Structural | Incomplete Response | Medium | GC | LGE | 2026-04-10 | 2026-04-27 |  |  | Regarding main steel BFA post review query of building-1
RFI #049 | Items Requiring EOR _LGE Clarification |  | Closed | Medium | GC | LGE | 2026-04-14 | 2026-05-06 |  |  | Items Requiring EOR _LGE Clarification
RFI #050 | Regarding main steel BFA post review query of building-2 |  | Closed | Medium | GC | LGE | 2026-04-17 | 2026-05-10 |  |  | Regarding main steel BFA post review query of building-2
RFI #051 | Connection Between Panel 22a and 22b Bldg 1 |  | Closed | Medium | GC | LGE | 2026-04-17 | 2026-04-27 |  |  | Connection Between Panel 22a and 22b Bldg 1
RFI #052 | Regarding Ledger Connection Between Panel-22A & 22B | Structural | Closed | Medium | GC | LGE | 2026-05-01 | 2026-05-11 |  | ✓ | Regarding Ledger Connection Between Panel-22A & 22B
RFI #053 | Door Jamb Post Install | Structural | Under Review | Medium | GC | LGE | 2026-05-08 | 2026-05-11 |  |  | Door Jamb Post Install
RFI #054 | Regarding Stair 1 Post BFA Query | Structural | Closed | Medium | GC | LGE | 2026-05-19 | 2026-05-18 |  |  | NOTE#1:- As per the BFA comment on Note #1, we understand that the stair-to-south wall dimension is 1'-5 7/8", the stair-to-north wall dimension is 8", and the total stair width (outer to outer) is 4'-0". However, based on the BFA comment on Note #2, the stair clear width of 3'-7" has been confirmed. Based on this clarification, we are considering the stair outer-to- outer width to be 4'-1" and revising the stair-to-north wall dimension to 7" instead of 8". Please see t | 1. Please proceed, stair is code compliant. 2. Please proceed with design intent, no substitution unless explicitly requested from design team.
RFI #055 | Regarding post install anchor at building-2. | Structural | Closed | Medium | GC | LGE | 2026-05-22 | 2026-05-23 |  |  | NOTE#1:- As per the AOR snap, we have kept a slab edge around the future stair opening. Due to this, we are required to shift the column at 2'-4" from Grid A.1 towards Grid-B (refer to Snap-1). Please note that this column is extending up to the roof level. Since the anchor bolts have already been cast, we will need to provide a post- installed anchor arrangement at this location. The proposed arrangement for the post- installed anchors is shown in Snap-2 & 3. Please confirm if this is a | Anchor bolts have not been installed
RFI #056 | Regarding Wedge Canopy Frame at Corners of Building | Structural | Closed | Medium | GC | LGE | 2026-05-26 |  |  | ✓ | NOTE#1:- After incorporating the BFA comments, the wedge canopy arrangement at the clouded corner-1 & corner-2 is appearing as shown in the attached references. A. For corner-1 the arrangement shown in Snap-1 is for Level-2, and the arrangement shown in Snap-2 is for the lower roof level. B. For corner-2 the arrangement shown in Snap-3 is for Level-2, and the arrangement shown in Snap-4 is for the lower roof level. Please review and confirm whether the proposed arrangement is ac
RFI #057 | Regarding Stabilizer Plate Angle for Joists | Structural | Closed | Medium | GC | LGE | 2026-05-26 | 2026-05-27 |  | ✓ | NOTE#1:- There is a conflict between the joist drawing and the design drawing: A. In Section 13/S105 of the design drawing, an L3x3x1/4 angle is provided to stabilize the bottom leg of the joist. B. However, in Sections 5 and 9 of the joist drawing, a stabilizer plate is specified. Currently, we are following the joist drawing and providing a stabilizer plate (PL 3/4" x 6" x 6"). Please confirm whether we are proceeding correctly or advise if any changes are requir | Proceed with 6x6x1/4"
RFI #058 | Column Shift for Self-Closing Gate Clearance | Structural | Closed | Medium | GC | LGE | 2026-06-16 | 2026-06-16 |  | ✓ | Per the RFI #45 response, the roof ladder height exceeds 30'-0", requiring the second-floor balcony to serve as an intermediate landing with a 3'-0" self-closing gate at the guardrail. To create the required gate opening at the Building-1 balcony, the column must shift north as shown on Sheet 601E123.
RFI #059 | Joist Splice Connection Bolts | Connections | Closed | Medium | GC | New Mill | 2026-06-18 | 2026-06-19 | ✓ |  | IFC drawings detail shows joist splice connection made with A490 hex head bolts. S&H Steel requests to furnish and install tension control (TC) bolts at all bolted joists and joist girder field splice connections, in lieu of standard hex structural bolts.S&H proposes the following assembly: - ASTM Grade F2280 (TC, A490-equivalent). Please confirm that TC bolts are acceptable for the field splice connection. Once a response has been received from New Mill, a copy will be forwarded to the GC/AOR/EOR for record. | Proceed with TC
RFI #060 | Regarding hangar door post brace support arrangement at building-2. | Structural | Under Review | Medium | GC | LGE | 2026-06-18 |  |  | ✓ | NOTE#1:- At the clouded location, the angle brace arrangement intended to support the hanger post is not feasible over the joist, because the joist is terminating before reaching the face of the return panel. Therefore, we have provided the brace support arrangement directly on the concrete panel using a 1/2" thick plate with TITEN HD screw anchor, as shown in Snap-1 and Snap-2. Please confirm whether this connection, as shown in Snap-1 and Snap-2, is acceptable. If not, please sug

## Schedule
Schedule
72 tasks · 43% complete · 1 delayed
WBS | Task | Type | Phase | Status | Priority | % Complete | Start | Finish | Crew | Milestone
2.1 | Anchor Bolts - Bldg. 1 & 2 | Submittal | Detailing | Complete | Normal | 100 | 0026-03-10 | 2026-04-02
1.1 | Project Kickoff | Task | Pre-Construction | Complete | Normal | 100 | 2025-12-02 | 2025-12-02
2.2 | Panel Embeds - Bldg. 1 | Submittal | Detailing | Complete | Critical | 100 | 2026-03-02 | 2026-03-25
2.3 | Joists / Deck - Bldg. 2 | Submittal | Detailing | In Progress | Critical | 0 | 2026-03-11 | 2026-06-30
2.13 | Panel Embeds - Bldg. 2 | Submittal | Detailing | Complete | Normal | 100 | 2026-03-13 | 2026-05-07
2.4 | Balcony Rail - Bldg. 1 | Submittal | Detailing | In Progress | Normal | 65 | 2026-03-23 | 2026-06-25
3.1 | Panel Embeds - Bldg. 1 | Task | Procurement | Complete | Critical | 100 | 2026-03-26 | 2026-03-31
2.6 | Main Steel - Bldg. 2 | Submittal | Detailing | Complete | Normal | 100 | 2026-03-31 | 2026-05-29
2.5 | Balcony Rail - Bldg. 2 | Submittal | Detailing | In Progress | Normal | 0 | 2026-03-31 | 2026-06-25
5.3 | Panel Embeds - Bldg. 1 | Delivery | Delivery | Complete | Critical | 100 | 2026-04-01 | 2026-04-07
4.3 | Panel Embeds - Bldg. 1 | Fabrication | Fabrication | Complete | Critical | 100 | 2026-04-01 | 2026-04-20
2.12 | Ladders - Bldg. 1 & 2 | Submittal | Detailing | Delayed | Normal | 0 | 2026-04-08 | 2026-04-22
6.1 | Panel Embeds - Bldg. 1 | Install | Installation | Complete | Normal | 100 | 2026-04-08 | 2026-04-08
2.8 | Joists / Deck - Bldg. 1 | Submittal | Detailing | Complete | Normal | 100 | 2026-04-14 | 2026-06-19
3.5 | Panel Embeds - Bldg. 2 | Task | Procurement | Complete | Critical | 100 | 2026-05-08 | 2026-05-13
2.11 | Stairs - Bldg 1 | Submittal | Detailing | In Progress | Normal | 0 | 2026-05-11 | 2026-05-18
2.12 | Stairs - Bldg. 2 | Submittal | Detailing | In Progress | Normal | 0 | 2026-05-11 | 2026-05-18
4.4 | Panel Embeds - Bldg. 2 | Fabrication | Fabrication | Complete | Critical | 100 | 2026-05-14 | 2026-06-02
2.13 | Main Steel (Wedge Canopy) - Bldg. 1 | Submittal | Detailing | Complete | Normal | 100 | 2026-05-14 | 2026-05-26
3.1 | Anchor bolt material | Task | Procurement | Complete | Normal | 100 | 2026-05-18 | 2026-05-23
4.2 | Anchor Bolts - Bldg. 1 & 2 | Fabrication | Fabrication | Complete | Critical | 100 | 2026-05-24 | 2026-06-12
2.13 | Site Misc. Steel | Submittal | Detailing | In Progress | Normal | 27 | 2026-05-26 | 2026-06-20
3.7 | Main Steel - Bldg. 2 | Task | Procurement | Complete | High | 100 | 2026-05-30 | 2026-06-04
3.8 | Building 2 Hardware | Task | Procurement | Complete | Normal | 100 | 2026-05-30 | 2026-06-03
3.12 | Truck 1 Delivery | Task | Procurement | Complete | Normal | 100 | 2026-06-02 | 2026-06-02
5.5 | Panel Embeds - Bldg. 2 | Delivery | Delivery | Complete | Critical | 100 | 2026-06-03 | 2026-06-28
4.10 | Main Steel - Bldg. 2 | Fabrication | Fabrication | In Progress | High | 0 | 2026-06-05 | 2026-06-25
5.3 | Truck 2 Delivery | Delivery | Delivery | Complete | High | 100 | 2026-06-06 | 82026-06-06
5.4 | Truck 3 Delivery | Delivery | Delivery | Complete | Normal | 100 | 2026-06-08 | 2026-06-10
2.14 | Wedge Canopy Mockups | Submittal | Detailing | Complete | Normal | 100 | 2026-06-12 | 2026-06-12
5.1 | Anchor Bolts - Bldg. 1 & 2 | Delivery | Delivery | Complete | High | 100 | 2026-06-13 | 2026-07-08
3.12 | Joists / Deck - Bldg. 1 | Task | Procurement | Complete | Critical | 100 | 2026-06-20 | 2026-06-20
4.5 | Joists / Deck - Bldg. 1 | Task | Fabrication | In Progress | Critical | 50 | 2026-06-21 | 2026-07-08
3.2 | Site Misc. Steel | Task | Procurement | Not Started | Normal | 0 | 2026-06-21 | 2026-06-26
3.2 | Balcony Rail - Bldg. 2 | Task | Procurement | Not Started | Normal | 0 | 2026-06-26 | 2026-07-01
5.6 | Main Steel - Bldg. 2 | Delivery | Delivery | Not Started | Normal | 0 | 2026-06-26 | 2026-07-21
3.2 | Balcony Rail - Bldg. 1 | Task | Procurement | Not Started | Normal | 0 | 2026-06-26 | 2026-07-01
4.9 | Site Misc. Steel | Fabrication | Fabrication | Not Started | Normal | 0 | 2026-06-27 | 2026-07-16
6.6 | Panel Embeds - Bldg. 2 | Install | Installation | In Progress | Normal | 72 | 2026-06-29 | 2026-06-29
3.5 | Stairs - Bldg. 1 | Task | Procurement | Not Started | Normal | 0 | 2026-07-01 | 2026-07-08
5.14 | Main Steel - Bldg. 1 | Delivery | Delivery | Not Started | Normal | 0 | 2026-07-01 | 2026-07-01
3.5 | Stairs - Bldg. 2 | Task | Procurement | Not Started | Normal | 0 | 2026-07-01 | 2026-07-08
3.2 | Roof Access Ladders - Bldg. 1 & 2 | Task | Procurement | Not Started | Normal | 0 | 2026-07-01 | 2026-07-08
3.13 | Joists / Deck - Bldg. 2 | Task | Procurement | Complete | Critical | 100 | 2026-07-01 | 2026-07-01
4.7 | Balcony Rails - Bldg. 1 | Fabrication | Fabrication | Not Started | Normal | 0 | 2026-07-02 | 2026-07-21
4.13 | Joists / Deck - Bldg. 2 | Task | Fabrication | In Progress | Critical | 37 | 2026-07-02 | 2026-07-11
4.8 | Balcony Rails - Bldg. 2 | Fabrication | Fabrication | Not Started | Normal | 0 | 2026-07-02 | 2026-07-21
4.7 | Main Steel - Bldg. 1 | Submittal | Fabrication | In Progress | Normal | 14 | 2026-07-02 | 2026-08-07
6.11 | Main Steel - Bldg. 1 | Install | Installation | Not Started | Normal | 0 | 2026-07-02 | 2026-07-12
4.5 | Roof Access Ladders - Bldg. 1 & 2 | Fabrication | Fabrication | Not Started | Normal | 0 | 2026-07-09 | 2026-07-14
4.12 | Stairs - Bldg. 2 | Fabrication | Fabrication | Not Started | Normal | 0 | 2026-07-09 | 2026-07-28
6.7 | Anchor Bolts - Bldg. 1 & 2 | Install | Installation | Complete | Normal | 100 | 2026-07-09 | 2026-07-09
4.11 | Stairs - Bldg. 1 | Fabrication | Fabrication | Not Started | Normal | 0 | 2026-07-09 | 2026-07-28
5.6 | Joists / Deck - Bldg. 1 | Milestone | Delivery | Complete | Critical | 100 | 2026-07-09 | 2026-07-09
6.2 | Joists / Deck - Bldg. 1 | Task | Installation | Not Started | Normal | 0 | 2026-07-10 | 2026-07-12
6.2 | Joists / Deck - Bldg. 2 | Submittal | Installation | Not Started | Critical | 0 | 2026-07-13 | 2026-07-15
5.15 | Joists / Deck - Bldg. 2 | Task | Delivery | Not Started | Critical | 0 | 2026-07-13 | 2026-07-13
6.15 | Joists / Deck - Bldg. 2 | Task | Installation | Not Started | Normal | 0 | 2026-07-14 | 2026-07-18
5.10 | Roof Access Ladders - Bldg. 1 & 2 | Delivery | Delivery | Not Started | Normal | 0 | 2026-07-15 | 2026-08-09
5.9 | Site Misc. Steel | Delivery | Delivery | Not Started | Normal | 0 | 2026-07-17 | 2026-08-11
5.8 | Balcony Rails - Bldg. 2 | Delivery | Delivery | Not Started | Normal | 0 | 2026-07-22 | 2026-08-16
5.7 | Balcony Rails - Bldg. 1 | Delivery | Delivery | Not Started | Normal | 0 | 2026-07-22 | 2026-08-16
6.9 | Main Steel - Bldg. 2 | Install | Installation | Not Started | Normal | 0 | 2026-07-22 | 2026-07-27
5.11 | Stairs - Bldg. 1 | Delivery | Delivery | Not Started | Normal | 0 | 2026-07-29 | 2026-08-23
5.12 | Stairs - Bldg. 2 | Delivery | Delivery | Not Started | Normal | 0 | 2026-07-29 | 2026-08-12
3.9 | Main Steel - Bldg. 1 | Task | Procurement | Complete | High | 100 | 2026-08-08 | 2026-08-13
6.9 | Roof Access Ladder - Bldg. 1 & 2 | Install | Installation | Not Started | Normal | 0 | 2026-08-10 | 2026-08-10
6.8 | Site Misc. Steel | Install | Installation | Not Started | Normal | 0 | 2026-08-12 | 2026-08-12
6.11 | Stairs - Bldg. 2 | Install | Installation | Not Started | Normal | 0 | 2026-08-13 | 2026-08-13
6.7 | Balcony Rails - Bldg. 2 | Install | Installation | Not Started | Normal | 0 | 2026-08-17 | 2026-08-17
6.6 | Balcony Rails - Bldg. 1 | Install | Installation | Not Started | Normal | 0 | 2026-08-17 | 2026-08-17
6.10 | Stairs - Bldg. 1 | Install | Installation | Not Started | Normal | 0 | 2026-08-24 | 2026-08-24

## Work Packages
Work Packages
15 packages · scoped by area & crew · 61% avg complete
WP # | Package | Phase | Status | % Complete | Area | Crew | Released | Start | Finish
WP-001 | Anchor Bolts - Bldg. 1 & 2 | Erection | Complete | 100 | Buildings 1 & 2 | Rouser | 2026-04-02 | 2026-04-06 | 2026-05-15
WP-002 | Panel Embeds - Bldg. 1 | Erection | Complete | 100 | Building 1 | Rouser | 2026-04-13 | 2026-04-17 | 2026-06-01
WP-003 | Panel Embeds - Bldg. 2 | Erection | Complete | 100 | Building 2 | Rouser | 2026-05-13 | 2026-05-13 | 2026-06-01
WP-005 | Joists & Deck - Bldg. 1 | Erection | In Progress | 80 | Building 1 | New Mill |  | 2026-06-19 | 2026-06-19
WP-006 | Balcony Rails - Bldg. 1 | Detailing | In Progress | 50 | Building 1 | Yashwant
WP-007 | Balcony Rails - Bldg, 2 | Detailing | In Progress | 50 | Building 2 | Yashwant
WP-008 | Roof Access Ladders - Bldg. 1 & 2 | Detailing | In Progress | 50 | Buildings 1 & 2 | Yashwant
WP-009 | Main Steel - Bldg. 1 | Fabrication | In Progress | 50 | Building 1 | Yashwant | 2026-05-20 | 2026-05-20 | 2026-07-01
WP-011 | Main Steel - Bldg. 2 | Fabrication | In Progress | 50 | Building 2 | Yashwant | 2026-05-29 | 2026-05-29 | 2026-06-12
WP-012 | Site Misc. | Detailing | In Progress | 30 | Buildings 1 & 2 | Yashwant
WP-013 | Stairs - Bldg. 1 | Detailing | In Progress | 50 | Building 1 | Yashwant
WP-015 | Stairs - Bldg. 2 | Detailing | In Progress | 50 | Building 2 | Yashwant
WP-016 | Remaining Embeds | Erection | Complete | 100 | Buildings 1 & 2 | S&H Shop
WP-017 | Joists & Deck - Bldg. 2 | Fabrication | In Progress | 50 | Building 2 |  |  | 2026-07-13 | 2026-06-26
WP-018 | Mock Up | Delivery | Not Started | 0

## Deliveries
Deliveries
13 loads · 1,849 pieces · 21.22 tons
Load | Description | Vendor | Status | Priority | Pieces | Tons | Area | Scheduled | Delivered
1 | Skyport at Redfield — Load 1 | S&H | Delivered | Normal | 496 | 4.616 |  | 2026-04-07 | 2026-04-07
2 | Skyport at Redfield — Load 2 | S&H | Delivered | Normal | 43 | 0.073 |  | 2026-04-14 | 2026-04-14
4 | Skyport at Redfield — Load 4 | S&H | Delivered | Normal | 29 | 1.905 |  | 2026-05-06 | 2026-05-06
6 | Skyport at Redfield — Load 6 | S&H | Delivered | Normal | 31 | 0.563 |  | 2026-05-08 | 2026-05-08
7 | Skyport at Redfield — Load 7 | S&H | Delivered | Normal | 202 | 1.53 |  | 2026-05-08 | 2026-05-08
5.1 | Skyport at Redfield — Load 5.1 | S&H | Delivered | Normal | 17 | 2.103 |  | 2026-05-12 | 2026-05-12
8 | Skyport at Redfield — Load 8 | S&H | Delivered | Normal | 125 | 0.319 |  | 2026-05-13 | 2026-05-13
9 | Skyport at Redfield — Load 9 | S&H | Delivered | Normal | 376 | 4.756 |  | 2026-05-13 | 2026-05-13
10 | Skyport at Redfield — Load 10 | S&H | Delivered | Normal | 14 | 2.162 | Building 1 | 2026-05-13 | 2026-05-13
11 | Skyport at Redfield — Load 11 | S&H | Delivered | Normal | 370 | 2.92 | Building 1 | 2026-05-14 | 2026-05-14
12 | Skyport at Redfield — Load 12 | S&H | Delivered | Normal | 126 | 0.269 |  | 2026-05-15 | 2026-05-15
| Mock Up | S&H | Scheduled | Normal | 0 | 0 | Building 1 | 2026-06-23
| Splice Plates (502M113) | S&H | Scheduled | High | 20 | 0 | Building 2 | 2026-06-25
TOTAL

## Fabrication
Fabrication & Production
Fab-release control — module structure + production rollup from the schedule
No fab-release records logged yet for this project.
SteelBuild Pro gates fabrication behind a server-side check (open RFIs / unapproved sets block release).
When releases are logged, each row carries: release #, work package, piece marks, piece count, tonnage, release & required dates.
FABRICATION PROGRESS · derived from schedule (Fabrication phase)
Fabrication Activity | Status | % Complete | Start | Finish
Panel Embeds - Bldg. 1 | Complete | 100 | 2026-04-01 | 2026-04-20
Panel Embeds - Bldg. 2 | Complete | 100 | 2026-05-14 | 2026-06-02
Anchor Bolts - Bldg. 1 & 2 | Complete | 100 | 2026-05-24 | 2026-06-12
Main Steel - Bldg. 2 | In Progress | 0 | 2026-06-05 | 2026-06-25
Joists / Deck - Bldg. 1 | In Progress | 50 | 2026-06-21 | 2026-07-08
Site Misc. Steel | Not Started | 0 | 2026-06-27 | 2026-07-16
Balcony Rails - Bldg. 1 | Not Started | 0 | 2026-07-02 | 2026-07-21
Joists / Deck - Bldg. 2 | In Progress | 37 | 2026-07-02 | 2026-07-11
Balcony Rails - Bldg. 2 | Not Started | 0 | 2026-07-02 | 2026-07-21
Main Steel - Bldg. 1 | In Progress | 14 | 2026-07-02 | 2026-08-07
Roof Access Ladders - Bldg. 1 & 2 | Not Started | 0 | 2026-07-09 | 2026-07-14
Stairs - Bldg. 2 | Not Started | 0 | 2026-07-09 | 2026-07-28
Stairs - Bldg. 1 | Not Started | 0 | 2026-07-09 | 2026-07-28
SHIPPED TO DATE
21.22 |  |  | 1,849 |  | 11
TONS DELIVERED |  |  | PIECES SHIPPED |  | LOADS DELIVERED

## Change Orders
Change Orders
2 approved · net $-26,935 to contract
CO # | Title | Status | Amount | Reason | Sched Days | Submitted | Approved
CO #001 | Deduct for Deleted Embeds | Approved | -4025.44 | Owner Request | 0 | 2026-04-20 | 2026-04-27
CO #002 | Deduct for SES / Rolling Gates | Approved | -22910 | Owner Request | 0 | 2026-04-20 | 2026-04-27
TOTAL
CHANGE NARRATIVE
CO #001 |  | Removal of (181) embed pieces, piece marks EM105, from project scope per the direction of Damon Spangle.
CO #002 |  | This Change Order is issued to remove the SES Gates and Rolling Gates from S&H Steel's scope of work. These items have been removed from the contract scope and will no longer be fabricated, supplied, or installed by S&H Steel Co.

## Financials
Financials
Lump-sum contract value, change-order adjustments & the AIA G702/G703 pay-app structure
CONTRACT SUMMARY
Original Contract Value |  | 1895403
Net Approved Change Orders |  | -26935.44
Adjusted Contract Value
Retainage (10%)
Contract Less Retainage
AIA G702 / G703 PAY APPLICATION
No pay applications submitted yet for this project.
SteelBuild Pro generates AIA G702/G703 applications from the Schedule of Values; figures use an integer-cents money model.
1 | Original Contract Sum |  | 1895403
2 | Net change by Change Orders |  | -26935.44
3 | Contract Sum to Date (Line 1 ± 2)
4 | Total Completed & Stored to Date |  | 0
5 | Retainage |  | 0
6 | Total Earned Less Retainage |  | 0
7 | Less Previous Certificates for Payment |  | 0
8 | Current Payment Due |  | 0
9 | Balance to Finish (Line 3 less Line 6)

## Vendors
Vendors
12 subcontractors, suppliers & service providers
Company | Type | Contact | Title | Phone | Email | State | Preferred | Terms | Status
Alliance Steel | Subcontractor | Jesus Mendivil | Owner | 602.703.8022 | alliancesteel.llc@outlook.com |  |  | Net 30 | Active
Amber Steel | Subcontractor | RH Bryant | Owner |  |  |  |  | Net 30 | Active
ASC Deck | Supplier | Kevin Wright |  | 916.420.0144 | kevin.wright@ascsteeldeck.com |  |  | Net 30 | Active
AV Deck | Subcontractor | April Velez |  | 602.571.1502 | april@avdeckinc.com |  | ✓ | Net 30 | Active
Canam | Supplier | Marc Reid |  | 480.639.8788 | marc.reid@cscsteelusa.com |  |  | Net 30 | Active
D&V Steel | Subcontractor | Hector Duran Jr. | Owner | 6029086837 | duranhr81@gmail.com |  | ✓ | Net 30 | Active
Empire Deck | Subcontractor | Greg |  | 720.934.0119 | greg.t@gwdeck.com |  |  | Net 30 | Active
FM Steel | Subcontractor | Michael Mulsow | Owner |  | m.mulsow@fmsteel.net |  |  | Net 30 | Active
HD Fabrication | Subcontractor | Steve |  |  | steve@hdfabandmach.com |  |  | Net 30 | Active
Lightning Steel | Subcontractor | Sergio Hernandez | Project Manager | 602.397.2266 | sergioh@lightningsteelerectors.com | AZ | ✓ | Net 30 | Active
New Millennium | Supplier | John Degidio |  | 909.208.2776 | john.degidio@newmill.com |  |  | Net 30 | Active
SOL | Service Provider | John Kinch |  | 480.734.5384 | john@sol-mail.net |  | ✓ | Net 30 | Active

## About
About this Workbook
What SteelBuild Pro is · module map · legends · data dictionary
WHAT IS STEELBUILD PRO?
SteelBuild Pro is a multi-tenant SaaS platform for structural-steel fabricators and erectors.
It runs the full project lifecycle: drawings → submittals → RFIs → work packages → fabrication →
delivery → erection, with cost, schedule and change-order control wrapped around the workflow.
Its moat is the Detailing Control Center: AI revision-diff, set-level approval, and an auto-lock that
releases drawing sets to fabrication the moment their submittal is approved.
THIS WORKBOOK
A read-only, presentation snapshot of one real project — Job 25531, Skyport at Redfield —
pulled live from the SteelBuild Pro database on June 22, 2026. Each tab recreates one app screen.
Figures are a point-in-time snapshot; the live app is the system of record.
SUBMITTAL STAGE FLOW
Not Started → IFA (In For Approval) → OFA (Out For Approval) → BFA (Back From Approval) →
OFS (Out For Scrub) → IFC (Issued For Construction) → Released for Fabrication.
R&R = Revise & Resubmit. Ball-in-court tracks who owns the next action (Detailer / EOR / GC / S&H / Owner).
STATUS COLOR LEGEND
Green = approved / released / complete / delivered. Teal = approved as noted.
Amber = in review / in progress / scheduled. Blue = active workflow stage.
Red = delayed / revise & resubmit / cost-or-schedule impact. Gray = not started / inactive.
DATA DICTIONARY · what each tab holds
Drawing Sets — packages tracked at set level (the unit of work), not individual sheets.
Drawings — individual sheets with stage & revision; partial revision uploads keep unlisted sheets current.
Submittals — the workflow authority; drawings.stage is deprecated for rollups.
RFIs — drawing_reference + cost/schedule impact flags; open RFIs can gate fab release.
Work Packages — released scope by area/crew; the bridge from detailing to the field.
Deliveries — truckloads with piece counts & tonnage. Change Orders — contract deltas with margin.
Fabrication & Financials — module structure shown; no records logged for this project yet.
Generated by Claude (Anthropic) from the SteelBuild Pro Supabase database · read-only demonstration · not the system of record.